## ICM Table
Information Category-Measureable Concept-Prospective Measures
| Information Categories | Measurable Concepts | Questions Addressed | Measures |  |  | Notes | References
|  |  |  | Prospective Indicators | Sample Base Measures | Measurement Specs |  |  | Action Items
Project | Schedule and Progress | Milestone Completion | Is the project or service meeting scheduled milestones? Are critical tasks or delivery dates slipping? | - Milestone Progress | - Number of milestones started and completed versus plan | Critical Path Performance [0 indicators] Milestone Dates [2 indicators] *3 extra indicators* | - Completion should be based on achieving specific quantifiable milestone completion criteria. - Milestones may include inch stones, or major critical milestones. - Might also look at critical path performance (slack time).
|  | Work Unit Progress | Are specific activities, products, and services completed as scheduled? | - Requirements Progress - Problem Reports Progress - Reviews Progress - Change Requests Progress - System Elements or Units Progress - Test Cases Progress - Action Items Progress - Service Deployment Progress - Service Level Agreement (SLA) Response Trends | - Requirements defined, traced, verified, validated - Problem reports discovered, closed - Reviews completed - Change requests opened, resolved - System elements or units designed, implemented, integrated, approved, qualified, accepted - Test cases developed, attempted, passed - Action items opened, completed - Service Deployments Completed | Action Item Status [1 indicator] Breadth of Test Measurement [1 indicator] Component Status [1 indicator] Depth of test [1 indicator] Design Completion [4 indicators] Effort vs Schedule [1 indicator] Feasibility of Plans [4 indicators (one from Milestone completion)] Design Progress [1 indicator] Test Procedure Maturity [1 indicator] Problem Report Status [5 indicators] Problem Reports open v c losed [1 indicator] Readiness for Delivery [4 indicators] Requirements Traceability [1 indicator] Requirements Status [0 indicators] Review Action Closure [3 indicators] Review Status [0 indicators] Schedule and Cost Pressure [1 indicator] Size-Schedule evaluation [1 indicator] Test Completion [4 indicators] Test Status [0 indicators] Work Product Approval Trends [1 Indicator] | - Other work unit progress measures may be defined based on the work in progress. - Other schedule performance indicators are included with financial performance indicators (e.g. earned value measures). - Each activity, service, and product must be defined with specific, measurable elements that are planned to be achieved. - "Achievement" must be defined with specific criteria to be verified as completed. | SELI Guide includes: - Requirements Verification Trends - "Requirements Validation Trends" - "Work Product Approval Trends" - "Review Action Closure Trends" - "Test Completion"
|  | Work Backlog | Is the backlog of work units growing? Has the backlog of work units been adequately addressed? | - Work Unit Backlog Trends - Burndown Rates | - Work units in backlog, work units in backlog resolved | System Definition Change Backlog [3 Indicators] | - Measure/categorize by priority level and age. - Work units may be: -- actions, assignments -- service requests -- story points or features -- maintenance actions -- open defects or open stakeholder problem reports | SELI Guide includes: - "Review Action Closure Trends" - System Definition Change Backlog Trends"
|  | Incremental Capability | Is capability being delivered as scheduled in incremental builds, releases, or service provisions? | - System Elements Integrated - Functionality Integrated - Services Deployed | - Systems elements integrated (planned versus actual) - Functions integrated (planned versus actual) - Services Deployed (planned versus actual) | Incremental Content [1 indicator] Incremental Content Functions [0 indicators]
| Resources and Cost | Financial Performance | Is the project or service meeting budget and schedule objectives? | - CPI, SPI Trends - Earned Value Cost and Schedule Variance - Budget Adequacy and Trends - Cost Trends | - Earned Value: -- Budgeted Cost of Work Scheduled (BCWS) -- Budgeted Cost of Work Performed (BCWP) -- Actual Cost of Work Performed (ACWP) -- Budget at Completion (BAC) -- Latest Revised Estimate (LRE) -- Estimate at Completion (EAC) - Budget, planned, and actual costs | Cost [2 indicators] Earned Value [1 indicator] Revenue [1 indicator] System Affordability [2 indicators] *3 extra indicators* | - For deployed systems, costs include those to operate, maintain (resolve problems), and enhance system. - Should include quantitative criteria to define completion and/or delivery of each work unit. |  | Note - look at current PMI terminology: planned value (PV), earned value (EV), actual cost (AC), budget at completion (BAC); see chapter 7 of 2008 PMI PMBOK. -- need to check 748 Standard - DOD standard
|  | Personnel Effort | Is effort being expended according to plan? Is there enough staff with the required skills? | - Staff Level Sufficiency - Effort Distribution and Trends - Skill Profiles - Staff Turnover Rates | - Number of staff on project and projected - Number of staff by skill level - Number of staff by activity - Staff added, removed, quit | Effort [3 indicators] HR Performance Incentives [1 indicator] Management Involvement [1 indicator] Size-Effort Evaluation [1 indicator] Staff Experience [1 indicator] Staff Turnover [0 indicators] SE Staffing Trends [1 indicator] *13 extra indicators* | - Can also focus on key staff. - Effort distribution and trends by activity provides a more detailed profile. - Look at these measures for the current state and future projection. - Skills includes expertise, experience, training, education, and domain knowledge. | SELI Guide includes: "Staffing and Skills Trends"
|  | Facilities and Support Resources | Are needed facilities, equipment, tools, and materials available as needed to meet milestones? | - Resource availability - Resource utilization | - Quantity needed, available - Time required, available, used | Facility Equipment Availability Trend [1 indicator] Resource Availability [0 indocators] Resource utilization [1 indicator] |  | SELI Guide includes: "Resource Volatility Trends"
| Risk | Technical Risk | Is the technical risk exposure at an acceptable level? Are the risk treatment actions performed per plan and are they effective? | - Risk Status - Risk Exposure Trends - Risk Treatment Trends | - Number risks by status and severity - Number risk treatment actions by status (new, in progress, closed) - Risk probability, impact, and criticality (to calculate exposure) | PI Risk Ratings [1 indicator] Risk Exposure [2 indicators] Risk Treatment [4 indicators] | - Risk Treatment is also referred to as Risk Handling. - Technical impacts of risks that are realized could also be quantified (e.g. performance impacts). - Opportunities can also be identified and tracked, as well as enablers for those opportunities to occur. | SELI Guide includes: - "Risk Exposure Trends" - "Risk Handling Trends"
|  | Cost and Schedule Risk | Is the project realistic within established cost and schedule parameters? Is the project at risk of exceeding acceptable cost and schedule objectives? | - Schedule Impact Risk Trends - Cost Impact Risk Trends | - Schedule risk - Cost risk |  | - Include updates as schedules and funding changes. - Develop a range of resource/Cost values with associated probabilities, not just one value. This facilitates improved awareness of potential resource/Cost exposure. - Cost impacts of risks that are realized could also be measured. - Could use the likelihood of exceeding specified percentage levels for cost and a specified number of months for schedule over the project baseline. | Various Government documents as well as other guidance, including: DI-MGMT-81650, Integrated Master Schedule; requires 3-point Schedule Risk Assessment;DI-MGMT-81466, Cost Performance Reports; requires 3-point EAC estimate; Peter Teets, USAF memo, Sept. 2004 and similar memo from John Young, Navy; USAF Material Command Financial Handbook references to “probability distribution associated with …cost”
| Size and Stability | Physical Size and Stability | How big is and how much change is occurring with the service or product's physical size, physical characteristics, or interfaces? | - System or Service Element Trends - Interface Complexity - Interface Compatibility - Lines of Code Trends | - System or service elements added, modified, deleted - Interface number (unique), complexity, growth, approval rates, changes, TBD/TBR closure per plan - Lines of code added, modified, deleted | Components [0 indicators] Database size [0 components] Interfaces [1 indicator] Lines of Code [2 indicators] Physical Dimensions [1 indicator] *6 extra indicators* | - Consider both internal and external interfaces. - System elements can include software or hardware elements. | SELI Guide includes: - "Interface Trends", which includes growth, approval rates, changes, TBD/TBR closure per plan, etc.
|  | Functional Size and Stability | How big is and how much change is occurring with the service or product's functional size, content, or logical characteristics? | - Requirements Trends - Architecture Element Trends - Functional Element Trends - Work Unit Backlog Size Trends - Function Points Trends - Call Center Request Trends - TBD/TBRs Trends - Desktop Deployment Trends | - Number added, modified, deleted | Function Points [0 components] Functional Change [2 indicators] Interface Trends [1 indicator] Function Point [2 components] Requirements Stability [1 indicator] Requirements [2 indicators] Requirements Trends [4 indicators] Requirements Validation trends [1 indicator] Requirements Verification [1 indicator] *10 extra indicators* | - This can be applied at any part or level of the system definition. - Functional architecture changes can be at the level of architecture description, model, or elements. - Call center requests can be categorized as problems or enhancements. | SELI Guide has: - "Requirements Trends", which includes growth, approval rates, changes, and TBD/TBR closure per plan - "System Definition Change Backlog Trends" - "Architecture Trends"
| Quality | Functional Correctness | Is the product or service good enough for delivery to the user? Are identified problems being resolved? | - Defect Profiles - Defect Density - Technical Measurement Trends - System Elements Accepted - Service Satisfaction Trend | - Defects by status, severity, priority, distribution, age, etc. - Technical measurement requirement, target, threshold, budget, and actual - System elements verified - Service Satisfaction Score | Age of Defects [1 indicator] Defect Error Trends [3 indicators] Defects [4 indicators] Maintainability [1 indicators] PI Technical Performance [1 indicator] Technical Measurement Trend [3 indicators] Technical Performance [0 indicators] *4 extra indicators* | Technical measurement includes Measures of Effectiveness, Measures of Performance, and Technical Performance Measures. | SELI Guide includes: "Technical Measurement Trends"
|  | Supportability - Maintainability | How much support does the system require? How difficult is it to support? | - Time to Restore - Mean-Time-to-Repair - Cyclomatic Complexity | - Hours to restore - Calendar hours and labor hours to repair - Number of paths through system | Cyclomatic Complexity [1 indicator] Maintenance Action [0 indicators] Time to Restore [2 indicators] *3 extra indicators* | Support includes maintenance, training, provision of supplies, etc. |  | Action Item: Team to identify any measures in use related to maintainability in software. (IEEE 1219 (Standard for Software Maintenance), Table 3, has some measures related to maintainability that apply to different life cycle activities (problem identification, analysis, design, implementation, system test, etc.). Measures of size and complexity and number of interfaces reflect maintainability as well. Action Item: Mauricio to send an example of adaptability - and documentation related to artifacts to understand the system and how to change it. Measure of how resilient the system is. Action Item: need to explore measures of coupling - any in common use? (review Linda Abelson's report on OO metrics) How about contacting George Stark for some items to include here? He's written papers on software maintenance Get definitions from John Musa’s Software Reliability Engineering book
|  | Efficiency | Does the target system or service make efficient use of resources? | - Utilization - Throughput - Response Time | - System or service element capacity available, used - Time for function (budget, actual) | Throughput [0 indicators] Timing [2 indicators] Utilization [0 indicators] *3 extra indicators* | It is important to capture benchmark times for key system functions. These can be reviewed as the system is maintained or altered, to ensure that no degradation occurs. |  | Should response time be timing?
|  | Portability | To what extent can the functionality be re-hosted on different platforms? | - Interface Compliance | - Interfaces verified | Standards Compliance [1 indicator] | Use of portability can also include reusability and adaptability.
|  | Usability | Is the user interface adequate and appropriate for operations? Are operator errors within acceptable bounds? | - User Interface Acceptability - Operator Error Trends | - Actions from user interface reviews - Operator errors | Operator Errors [3 indicators] |  |  | Action Item: Earthy: See ISO 9241-11 Guidance on Usability
|  | Dependability - Reliability | How often is service to users interrupted? Are failure rates within acceptable bounds? | - Mean-Time-to-Failure - Availability | - System or service element failures by severity, priority - Element start, end times | Failures [2 indicators] Fault Tolerance [no indicators] Maintenance Status [4 indicators] *1 extra indicator* | Instead of availability, might measure downtime (outages).
|  | Security - Safety | How many vulnerabilities are identified and remediated by life-cycle phase? How many relevant attack patterns have been covered by test cases? | - Profile of vulnerabilities - Cost to fix vulnerabilities - Attack Pattern Test Coverage Profile | - Vulnerabilities discovered, remediated - Cost to fix vulnerabilities - Test cases developed, verified per attack pattern |  |  |  | Action Item: LSaleski - send examples of the Security categories.
| Process Performance | Process Compliance | How consistently does the project implement the defined project and enterprise processes? | - Process Reference Maturity/Capability Rating - Process Audit Findings Distribution | - Maturity/Capability Rating Goal, Assessed - Number of audit findings by process area | Architecture trend [1 indicator] Process Audit Findings [1 indicator] Process Compliance Trends [3 indicator] Reference Model Rating [2 indicators] *7 extra indicators* |  | SELI Guide includes: "Process Compliance Trends"
|  | Process Efficiency | Are the processes efficient enough to meet current commitments and planned objectives? | - Productivity Performance Trends - Cycle Time Performance Trends | - Work unit size - Effort expended - Elapsed calendar and time expended | Cost of Quality [1 indicator] Cycle Time [1 indicator] Productivity [2 indicators] Tailoring Difficulty [1 indicator] *8 extra indicators* | For agile developments, team velocity is a measure of productivity.
|  | Process Effectiveness | Are the processes generating the results expected? How much rework is occurring? | - Defect Containment - Test Effectiveness - Test Coverage - Defect-prone system elements distribution - Operational and Maintenance Effectiveness - Rework Effort Distribution - Rework System Elements Trends | - Defects by phase injected, discovered, and resolved (defect propagation) - Defects discovered per test case and test type - Defects discovered per system element - Schedule and effort expended - total and rework - System or service elements requiring rework | Defect Containment [1 indicator] Defect Containment (PCRs) [1 indicator] Rework [2 indicators] | - Defects per system element is particularly important for key elements of the architecture, or if safety/security related. - For services, schedule and effort expended might include those related to service calls. - Rework in production might measure waste of production units - Could also measure benefits of processes (e.g. cost prevention) - Defect containment is also called "Defect Escapes" |  | Action: Team to provide any examples of actual measures in use. * discovery and fix cost at some point in the lifecycle, e.g., after delivery to the customer, can be represented in terms of process averages * potential cost of residual defects can similarly be estimated in terms of process averages * each process improvement implemented carries a measurable change in, e.g., cost performance.
| Technology Effectiveness | Technology Suitability | Can technology meet all allocated requirements, or will additional technology be needed? | - Requirements Coverage | - Requirements met by technology | Requirements Coverage [2 indicators]
|  | Technology Maturity | Is the technology ready to be used in this project? | - Technology Maturity Trends | - Technology readiness level (TRL) | Technology Maturity Trends [1 indicator] | Might also consider technology obsolescence - is the technology about to become obsolete?
|  | Technology Volatility | Does new technology pose a risk due to too many changes? | - Technology Baseline Changes Trends | - Number of requirements impacted by changed technology | Baseline Changes [2 indicators] Technology Impact [3 indicators]
| Customer Satisfaction | Customer Feedback | How do our customers perceive our performance for individual projects and the enterprise? Are we meeting user expectations? | - Satisfaction Ratings Trends - Award Fee Distributions | - Satisfaction ratings - Award fees received | Survey Results (1 indicator) Customer Satisfaction with Service or Product (copyrighted) (no indicator) Award Fee Score (2 indicators) Performance Rating [2 indicators] | - Contractor Performance Assessment or other survey - Could also count number of positive or negative reports from customers |  | Action Item: CPAR is another commonly used measure of customer feedback (Bill Golaz: please provide example)
|  | Customer Support | How quickly are customer support requests being addressed with respect to our target cycle time? How do customers perceive our customer support response? | - Support Request Distributions - Support Time Trends | - Number of support requests - Calendar time to address requests | Requests for Support (2 indicators) [Question: should the time component be moved to support time, or should there just be one specification] Support Time (1 indicator) Market Share [1 indicator] | The assumption is that the customers' ability to use the service or product supports customer satisfaction.
Enterprise | Schedule & Progress | Milestone Completion | Are the projects or services within this enterprise on track? Which activities need management attention (which ones are most behind)? | - Enterprise Milestone Status | - Number of milestones started and completed versus plan (percent complete versus plan) |  | - Milestones mean major milestones or sum of set of milestones. - An enterprise needs some early indication of whether major milestones will be met, for each project in the enterprise (or those strategically important or those most at risk).
|  | Work Backlog | What is the enterprise work backlog? What should be scheduled next? | - Work Unit Backlog Trends - Burndown Rates | - Work units in backlog by priority level for major item - Work units in backlog resolved |  | Work units may be: - open stakeholder requests - defects - enhancements, needs - tasks - new contracts, RFPs - deliveries
| Resources & Cost | Financial Performance | Is the enterprise receiving and spending money as planned? Does the enterprise financial process support the needs of the projects? Is the enterprise meeting its goals and objectives? | - Funding Availability - Disbursement / Obligation Rate Trends - Earnings Progress - Return on Investment Capital | - Budget, planned, and actual funds available - Disbursements, obligations - Sales, costs, incentive/award fees, taxes - Contribution to overhead - Invested capital, additional revenue |  | Is funding available as needed? Consider: - spread of money across the year for multiple projects - color of money and plus-ups for government projects - funding blocks, pull-backs - studies, management reserve, as well as development and maintenance projects
|  | Personnel Effort | Within the enterprise, are there sufficient qualified people to satisfy commitments? | - Staff Level Sufficiency - Effort Distribution and Trends - Workforce Skills Profiles - Workforce Age Profiles - Staff Turnover Rates | - Number of staff within enterprise - Number of staff by skill level and project, needed and assigned to project - Number of staff by age - Staff added, removed, quit |  | - Both a project and enterprise issue. - Skills includes expertise, experience, training, education, and domain knowledge.
|  | Facilities and Support Resources | Are needed facilities, equipment, tools, and materials available, across the enterprise? Where should future investments occur? | - Resource availability - Resource utilization | - Quantity needed, available - Time required, available, used |  | For the aggregate set across all projects.
| Risk | Technical Risk | Is the technical risk exposure for the enterprise at an acceptable level? Do we have a balanced risk/reward portfolio? | - Portfolio Risk Status - Risk Tolerance | - Number risks by status and severity |  | Should also consider enterprise risks, in addition to assessing aggregate risks across projects. |  | Action: Cheryl to look at how widespread enterprise risk management (more than just project aggregation.
|  | Cost and Schedule Risk | Is the enterprise at risk of exceeding acceptable cost and schedule objectives? | - Schedule Impact Risk Profile - Cost Impact Risk Profile | - Schedule Risk - Cost Risk
| Size & Stability | Physical Size and Stability | How big is and how much change is occuring with the physical size, physical characteristics, or interfaces? | - Platform/System/Service Trends -Interface complexity -Interface compatibility -Lines of Code trends | - Number of unique platforms, systems, or applications - Number of unique interfaces, complexity, growth, changes
| Quality | Functional Correctness Dependability-Reliability | Is the set of projects delivering quality products or services that meet user expectations? Are known problems being resolved? | - Stakeholder Defects Distribution - Warranty Trends | - Defects by status, severity, priority, distribution, etc. - Warranty claims |  | Stakeholder defects are those identified after fielding.
| Process Performance | Process Compliance | Are enterprise processes being applied across the enterprise? | - Reference Maturity/Capability Profile - Process Audit Findings Distribution - Exception Distributions | - Maturity/Capability Rating Goal, Assessed - Number of audit findings by process area - Number of exceptions by process element |  | Exceptions include waivers and amount of tailoring.
|  | Process Efficiency | What are enterprise norms for completing life-cycle activities (schedule, cost, performance)? Do the majority of projects meet the norms? | - Productivity Baselines and Trends - Cycle Time Baselines and Trends | - Work unit size - Effort expended - Elapsed calendar and time expended
|  | Process Effectiveness | Are the enterprise processes sufficient to accomplish enterprise objectives? How much rework is occurring? | - Rework Effort Distribution | - Schedule and effort expended - total and Rework
| Technology Effectiveness | Technology Maturity | Does the enterprise have sufficient technology management plans and implementations? Is technology investment in place to ensure adequate leverage of technology into projects or services? | - Technology investment versus plan - Needs Met by Technology Insertion - Technology Refresh Rate | - Investment amount - Number of needs met by inserted technology - Technologies replaced |  | Needs met includes new and enhanced capabilities proven in test
| Customer Satisfaction | Customer Feedback | How do our customers perceive value with the enterprise's set of services or products (product lines)? Are they meeting user expectations? | - Satisfaction Ratings Trends - Market Share | - Satisfaction ratings - Enterprise sales, total market sales, new contracts awarded - Assessed value |  | - Generally measured through a survey.
Note on E3: Indicators are often trends over time of planned versus actual values. They might also be represented as rates, status as of one date, comparisons between attributes or entities, or other relationships.
Note on F3: In most cases, date/time is captured for each base measure, so is not included in these listings. Most base measures include both planned and actual values.
Note on E23: John Sautter: Moved SLA to Progress

## Definitions
| Definitions (adopted from 15288:2008) | Notes
System Elements | member of a set of elements that constitutes a system NOTE A system element is a discrete part of a system that can be implemented to fulfill specified requirements. A system element can be hardware, software, data, humans, processes (e.g., processes for providing service to users), procedures (e.g., operator instructions), facilities, materials, and naturally occurring entities (e.g., water, organisms, minerals), or any combination. | In this ICM Table, we use the term "System Elements" to indicate the partitioning of the system into lower level elements. Other terms that are commonly used include subsystem, component, increment, function, etc.
Enterprise | person or a group of people and facilities with an arrangement of responsibilities, authorities and relationships [15288:2008 definition for "organization"] NOTE 1 Adapted from ISO 9000:2005. NOTE 2 A body of persons organized for some specific purpose, such as a club, union, corporation, or society, is an enterprise NOTE 3 An identified part of an enterprise (even as small as a single individual) or an identified group | In this ICM Table, we use the term "Enterprise". Other sources uses the term organization. Some sources use the term enterprise for the top-level, and organization for lower-level elements, while others reverse these terms. We use enterprise for any level, as a global term.
Acquirer | stakeholder that acquires or procures a product or service from a supplier NOTE Other terms commonly used for an acquirer are buyer, customer, owner, or purchaser.
Stakeholder | individual or organization having a right, share, claim, or interest in a system or in its possession of characteristics that meet their needs and expectations
Supplier | organization or an individual that enters into an agreement with the acquirer for the supply of a product or service NOTE 1 Other terms commonly used for supplier are contractor, producer, seller or vendor. NOTE 2 The acquirer and the supplier may be part of the same organization.

## Measurable Concept Description
# | Information Categories | Measurable Concepts | (Almost) Final Revised Description
1 | Schedule and Progress | Milestone Completion | The Milestone Performance measures provide schedule and progress information for key development activities and events. The measures also help to identify and assess dependencies among development activities and events. Monitoring schedule changes helps to assess the risk in achieving future milestones.
2 |  | Work Unit Progress | Work Unit Progress measures address progress, based on the completion of hardware or software elements that combine incrementally into a complete activity or product. If objective completion criteria are defined based on a pre-established project plan, Work Unit Progress measures are very effective for assessing progress at any point in the project. They can be used to estimate completion dates for activities or products .
3 |  | Work Backlog | Work Backlog refers to an accumulation of new or unfinished work over time. It quantifies the amount of work remaining at the end of a particular time period, and is often represented in a burndown chart. It may include base measures of unresolved defects (systems testing), open stakeholder problem reports, open service requests (services), story points or features not yet implemented (agile), open actions or assignments, or maintenance actions. Work Backlog may impede progress, quality, or schedule. It may also provide an indication of potential rework due to solutions not being available in a timely manner.
4 |  | Incremental Capability | Incremental Capability measures count the cumulative functions or product elements associated with a product at a given time. An increment is a predefined group of work units, functions, or product elements. An increment may be a product shipped to a customer or an internal increment delivered to the next phase of the life cycle. These measures determine whether the capability is being developed as scheduled or delayed to future deliveries. The measures can also support decisions on product release.
5 | Resources and Cost | Financial Performance | Financial Performance measures report the difference between the budgeted and actual cost of work performed to the budgeted cost of work scheduled for a specific product or activity. These measures are used to assess whether the project can be completed within cost and schedule constraints, and to identify potential cost and schedule overruns.
6 |  | Personnel Effort | Personnel measures characterize the amount of effort that is planned and expended. These measures may also describe the number and experience of personnel assigned to a project and may evaluate the rate at which people are added to and removed from a project. Personnel measures can be used to assess the adequacy of planned effort and to analyze the actual allocation of labor. They are essential to evaluating development productivity. These measures assist the enterprise in making essential training, coaching, and hiring decisions to ensure the workforce is capable of meeting both current needs and projected future needs.
7 |  | Facilities and Support Resources | Facilities and Support Resources measures address the availability and utilization of tools, spare parts, and facility resources (they do not include Personnel). Resources may include measures for development, integration and test, file build, operations and maintenance. These measures address the adequacy of resources and are recommended for projects where key resources are shared with other projects, or are suspected to be inadequate.
8 | Risk | Technical Risk | Technical Risk measures quantify the effect of events in the project that have a negative risk exposure (a non-zero probability of occurrence and an unfavorable consequence on technical performance or quality). Technical risks can occur at any time in the lifecycle and can lead to a technical solution that does not meet specified requirements or mission needs. Technical Risk measures refer to the exposure to loss arising from activities such as design and engineering, manufacturing, technological processes and test. They describe the set of technical problems associated with a new or emerging technology. Those problems can arise from application of a new process, material, or system element before fully understanding the parameters that control performance, cost, safe operating latitudes, or failure modes. They can occur if a previously commercialized technology is extended outside the known domains of the pertinent design rules. They can also occur from unexpected interactions arising from a new or unique combination of system elements.
9 |  | Cost and Schedule Risk | Cost and Schedule Risk measures provide a quantitative assessment of the risk associated with the estimated cost to complete scheduled activities and the time allowances for the activities or project as a whole. Those risks may be expressed as ranges, with the width of each range indicating the degree of risk. They may also be expressed as probability distributions, with a probability of occurrence corresponding to each value or range of values.
10 | Size and Stability | Physical Size and Stability | Physical Size and Stability measures quantify the physical size of a system, product, or enterprise. Size is a critical factor for estimating schedules and costs. These measures also provide information on the amount and frequency of change to systems, products, or enterprises. Late changes are especially critical in system or product developments.
11 |  | Functional Size and Stability | Functional Size and Stability measures quantify the functionality of a system or product based on the Functional User Requirements. Functional size may be used to estimate development schedule and cost. These measures also provide information about the amount and frequency of change to the system’s functionality, which is critical late in development. Functional changes generally correlate to effort, cost, schedule, and product size changes.
12 | Product Quality | Functional Correctness | Functional Correctness measures identify the accuracy that is achieved in product functions and the number of functional defects that are observed. These measures provide an indication of product quality and readiness for delivery and operations.
13 |  | Supportability - Maintainability | The measures of Supportability - Maintainability quantify the time and level of resources that are required to sustain the useful life of a system and its elements through planned restoration and enhancement. Supportability - Maintainability measures also quantify resources that are needed to restore a system to operational status after a failure. These resources include tools, personnel, repair parts, and other assets. Supportability - Maintainability measures help evaluate the users’ ability to sustain system operation during the time required to complete a mission or task. These measures are determined by the specific characteristics of the system such as the complexity of elements, the number and intricacy of the interfaces, the degree of nesting, and the types of data structures. Complex or tightly coupled elements are more difficult to restore or repair after failure. Complex elements are generally harder to test and, may contain more defects and more resources to maintain than less complex components.
14 |  | Efficiency | Efficiency measures are used to assess operational adequacy regarding required resources, output generated, or timing of the system and its elements (software and hardware). Efficiency measures have implications for system performance, cost, enhancement, and supportability. During development, measures focus on the reserve capacity of elements to ensure adequate performance under stress conditions and to permit future growth from new requirements. Systems with low efficiency (high utilization or low throughput) often require a costly upgrade after deployment and operation.
15 |  | Portability | Portability measures address the interface and interoperability of a system element to determine the feasibility and resources needed to modify the element for use in another application. The measure may help predict and assess the ability to move software applications or hardware elements within the system environment or between systems. These measures also assess compliance with recognized standards. The level of open systems compliance and lack of proprietary vendor design characteristics may indicate software portability.
16 |  | Usability | Usability measures predict and assess the capability of the product to be understood, learned, used and attractive to the user. Users may include operators, end users and indirect users who are under the influence of or dependent on the use of the product. The measures are based on factors such as system safety, consistency, reliability, and adequacy of documentation. Usability measures may also assess readiness to deliver.
17 |  | Dependability - Reliability | Dependability - Reliability measures estimate the probability that an item will maintain a specified level of performance for a specified period of time under certain conditions. Reliability is the probability that an item will function without failure for a specified period of time under certain conditions. Availability is related to Dependability - Reliability. Failures that occur during operation either degrade or completely eliminate certain functions, some of which could be mission critical or safety hazards. These measures monitor the quantity and severity of failures, and determine if the expected frequency of failures is acceptable. Estimated probabilities of failures and consequences can be determined through modeling, analysis, and/or testing.
18 |  | Security - Safety | Security - Safety measures quantify the level of confidence that a system element is free from vulnerabilities, either intentionally designed into the system element or accidentally inserted at anytime during its lifecycle, and that the system element functions in the intended manner. While Security focuses on the ability of a system to prevent unauthorized access, whether accidental or deliberate, to programs and data, Safety focuses on the conservation of human life and its effectiveness, and the prevention of damage to items, consistent with mission requirements.
19 | Process Performance | Process Compliance | Process Compliance measures address compliance of an enterprise's process to either a standard process assessment model or to the enterprise's policies and procedures. “Process” describes the people, methods, and tools that are used to generate the organization's products. “Process component" describes any specific procedure or resource that is established within an organization's process and is measured in a process assessment. These measures identify strengths and weaknesses of an organization’s process and monitor progress towards improvement of the process. Although many process assessment models exist, the most common are the Capability Maturity Model Integration (CMMI), developed by the Software Engineering Institute and ISO/IEC 15504, Process Assessment. Process Compliance measures may also be obtained from the results of audits that are based on the International Organization for Standardization (ISO) 9000 series of Quality Management standards.
20 |  | Process Efficiency | Process Efficiency measures monitor how well the project uses resources to perform its tasks. A goal of process improvement is to increase efficiency by enhancing process performance without compromising the quality of the product. Process Efficiency is typically increased through reduced costs, reduced variability, and reduced cycle time. Process Efficiency measures may quantify the resources consumed in the process relative to minimum possible levels. They may also relate resources consumed to output levels.
21 |  | Process Effectiveness | Process Effectiveness describes what is produced in relation to what is needed or expected. Process Effectiveness measures quantify process performance and the consequences of poor performance. Every process has specific goals, and measures must relate to these goals. An ineffective process results in poor product quality or rework to fix the product. Process Effectiveness is increased by improving the products or services (outputs) delivered. Depending on the situation, improvement may be achieved through redesigning the process or redesigning the product or service. Low rework level and high defect containment are indications of high Process Effectiveness.
22 | Technology Effectiveness | Technology Suitability | The Technology Suitability measures quantify the degree to which system requirements can be achieved by proposed technical solutions. These measures evaluate system element characteristics that can be quantified during software/system selection and testing phases. These measures assess the overall ability of a candidate technical solution or existing technology to meet the users’ requirements. Technology Suitability measures also provide insight into performance and interoperability issues. Cost, schedule, or resource constraints often drive changes that affect technology insertion. Changes to functional requirements may affect a technology’s suitability for the solution. Likewise, changes in the technology (or product) may cause the candidate solution to be less suitable. Problems in system performance and interoperability may be caused by several factors, including requirements mismatch, unacceptable behavior, incompatibility among products, overlap or gaps in functionality, technology application shortfalls, incomplete products, or vendor inflexibility. Suitability measures may identify where redesign is needed for another technology to solve compatibility issues.
23 |  | Technology Maturity | Technology Maturity measures quantify the level of maturity, including readiness and obsolescence, of specific technologies under development. These measures indicate that technology opportunities exist that need to be examined and may warrant product changes. They also indicate when a technology is becoming obsolete and may be a candidate for replacement.
24 |  | Technology Volatility | Technology Volatility measures quantify a product’s rate of change after the implementation of a technology. These measures provide insight into the relative maturity of a particular technology and the susceptibility of a technology to obsolescence. Other issues to consider that relate to technology volatility include product obsolescence, new version transition, interaction of products with different upgrade cycles, licensing and support costs, vendor viability, and product replacement. The measures in this category support decisions on whether to adopt the technology, when to adopt the technology, and when to replace the technology.
25 | Customer Satisfaction | Customer Feedback | Customer Feedback measures are used to obtain direct customer satisfaction information. Generally, these measures are applied at a project level or aggregated at the enterprise level. Customer satisfaction includes delivering products that meet the specified requirements, that are built on time and within budget (contract-driven efforts), or that are reasonably priced (market-driven efforts). Customer satisfaction is highly dependent on customer perceptions of whether or not the product, system, or service meets needs and expectations (rather than specified requirements alone) and provides a pleasant and efficient user experience.
26 |  | Customer Support | Customer Support measures quantify the utilization and responsiveness of the organization’s customer support function. These measures monitor the effectiveness of the support response and its impact on customer satisfaction. Customer Support measures reveal the number and impact of problems on users and provide feedback on overall product satisfaction.

## Measure Descriptions
| Information Categories | Measurable Concepts | Measures
|  |  | Indicators | New Revised Description | Notes: (to cover in specification)
Project
Schedule and Progress
Milestone Completion
|  |  | Milestone Progress | The Milestone Completion measure provides insight into whether milestones are proceeding according to plans. Progress is measured in terms of inch stones (artifacts and events) that relate to the requirements. Comparison of planned and actual milestone dates provides insight into significant and repetitive schedule changes at the activity level.
|  | Work Unit Progress |  |  | If you don’t pay attention to the quality of the tasks or products, your progress measures are going to give you false information. Defining explicit exit criteria for each work unit progress measure helps to address this issue.
|  |  | Requirements Progress | The Requirements Progress measure counts the number of expected requirements that have been defined and allocated to hardware and software elements. and evaluates actual completion status. It can also count the number of defined requirements that have been allocated to test cases, and the number that have been successfully tested, This measure provides an indication of progress towards completion. | Requirements verified, may be evaluated during dry run as well as during formal testing. Magnitude of time spent performing development and dry running of test cases often causes slips in higher level schedules and milestones.
|  |  | Problem Reports Progress | Problem Report Progress counts the number of system, hardware, or software problems reported and resolved. This measure provides an indication of product maturity and readiness for delivery. The rates at which problem reports are written and resolved can be used to estimate product completion. This measure can also indicate the quality of the problem resolution process, based on the average age of reported problems and the average time to resolve them | In the specification, need to discuss having an attribute for the criteria for closing a PR. PRs should not be counted as closed until the resolution has been verified (versus when it is assigned to someone for resolution).
|  |  | Reviews Progress | The Reviews Progress measure tracks the number of reviews successfully completed against plan, including both supplier and acquirer reviews. The measure provides an indication of progress in completing review activities. | In specification, need to address measurement of partial progress. It is best to measure actuals against exit criteria that include not only holding the review, but also closing out and verifying identified action items and problem reports.
|  |  | Change Request Progress | The Change Request Status measures the change requests that affect a product over time. The measure provides an indication of the amount of rework that has been performed or will be required. This measure only identifies the number of changes; it does not report on the functional impact of changes or the amount of effort required to implement them.
|  |  | System Elements or Units Progress | The System Elements or Units Progress measure counts the number of system elements or units that complete a specific activity. System Elements or Units Progress might include design elements developed, integrated, or tested; software or hardware components developed, tested, or integrated; test cases or steps attempted and successfully completed; Maintenance Actions; etc. A comparison of plans and actuals helps assess progress. Early in the life cycle, planning changes should be expected. Later in the process, an increase in the planned number of system elements that are scheduled for a specific activity may indicate unplanned or excessive growth.
|  |  | Test Cases Progress | The Test Status measure counts the number of planned test cases and compares it with test cases that have been attempted and the test cases that have been completed successfully. Test cases attempted may include both dry run and/or formal testing. This measure provides an indication of progress towards completion. | Specification should include an example where dry run progress is a separate base measure in the indicator. Make sure example shows both progress in attempted (versus plan), and also in successful completion (verses both plan and attempted).
|  |  | Action Items Progress | The Action Item Status measure reports the number and status of action items for technical and management activities. This measure provides information on the total number of open action items, as well as the number opened or closed during the reporting period. Analyzing trends of opened and closed items is effective in evaluating progress. This measure may be able to provide leading indication of achieving the schedule.
Work Backlog
|  |  | Work Unit Backlog Trends | This measure tracks trends in the number of work units, over time, to help assess the quantity of work remaining for a given product. This could be actions or assignments, service requests, story points or features, maintenance actions, open defects or open stakeholder problem reports, or functional changes. This information helps to assess what types of items are lagging, or taking longer to be addressed than planned. It quantifies the trends related to growth and change of the work backlog. Work Backlog may impede system definition progress or system development quality/schedule. It may also provide and indication of schedule risk and potential rework due to changes not being available in a timely manner.
|  |  | Burndown rates | The burndown rate measure indicates the "velocity" of a team to finish the tasks or work units planned for a certain period. It can be used to assess how a team is doing toward meeting their goal, or if a release will be on time with the quality and functionality desired. Burndown rate can also show how the team performance has been affected by the introduction, change, or removal of tasks or work units.
Incremental Capability
|  |  | System Elements Integrated | The System Elements Integrated measure indicates progress in integrating the system elements into defined increments. An increment represents a version of the final end capability or product. Increment content is often deferred or removed to preserve the scheduled delivery date. It is easier to track incorporation of capability by system elements (rather than by functionality) since it is relatively easy to detect whether or not a system element has been completed and integrated. It requires a plan be defined documenting which functional capability is to be provided in each incremental release.
|  |  | Functionality Integrated | The Functionality Integrated measure identifies progress in integrating the functional content of increments. The measure indicates progress in incremental functionality based on the requirements planned for the final end capability or product. Increment content is often deferred or removed to preserve the scheduled delivery date. It requires a defined plan of what functional capability is to be provided in each incremental release.
Resources and Cost
|  | Financial Performance |  |  | ANSI/EIA-748, Earned Value Management Systems, June 2007 is the widely-accepted standard for the Earned Value financial reporting system. Earned Value Management uses a baseline of planned cost for each unit of work that is scheduled to be performed, the Budgeted Cost of Work Scheduled (BCWS). Financial Performance is monitored by comparing the planned baseline (BCWS) to the Budgeted Cost of Work Performed (BCWP) and the Actual Cost of Work Performed (ACWP).
|  |  | CPI, SPI Trends | CPI, SPI Trends provide an indication as to whether work is proceeding according to plan from a cost and schedule perspective. CPI Trends shows the ratio of actual cost of work performed to the budget, based on dollars budgeted for each component of the WBS. It provides an indication of whether the project costs more or less than planned. SPI Trends shows the ratio of the budgeted cost of work performed to the scheduled budget, based on dollars budgeted for each component of the WBS. It provides an indication of whether the project schedule is on track. The measure can identify cost and schedule overruns and under-runs early in a project. | The cumulative ratio of budgeted cost and schedule to actual achieved values is computed as: Cost Performance Index (CPI) = BCWP / ACWP Schedule Performance Index (SPI) = BCWP / BCWS Both of these measures are with respect to the Earned Value mechanism that is in place.
|  |  | Earned Value Cost and Schedule Variance | The Earned Value measure provides insight into whether Work Breakdown Structure (WBS) elements are proceeding according to plan from a cost and schedule perspective. This measure provides the percentage amount (in dollars) of any cost or schedule differential. | Financial Performance is measured in terms of percentage variance from plan (BCWS), as: Schedule Variance = (BCWP - BCWS) / BCWS Cost Variance = (BCWP - ACWP) / ACWP
|  |  | Budget Adequacy and Trends | The Budget Adequacy and Trends measure evaluates the executability of a project: that is, the adequacy of the budget and schedule given the amount of work that is to be accomplished. Volatility in Budget Trends is an indication of risk and often leads to requirements changes or schedule delays. | Budget adequacy should be evaluated before the RFP is released (to ensure adequate funding, given the specified requirements), at contract award (to ensure that negotiations and requirements changes have not impacted budget adequacy), and any time there are significant requirements changes, budget changes, or schedule slippages. Budget volatility should generate associated risks.
|  |  | Cost Trends | The Cost measure counts budgeted and expended costs. The measure provides information about the amount of money spent on a project or a product, compared to budgets. | Note: This is used for projects that do not collect earned value, but instead track budget versus expenditures.
Personnel Effort
|  |  | Staff Level Sufficiency | The Staff Level Sufficiency measure determines a project team's skill level and experience level with respect to a defined area or domain, against the project requirements. This measure could also address the quantity of training and years of experience in a particular domain or subject matter. Data may be evaluated by depth of expertise (Novice, Apprentice, Journeyman, Master, etc.).
|  |  | Effort Distribution and Trends | The Effort measure counts the number of labor hours or number of personnel applied to all tasks, against the plans. It can be categorized by activity as well as by product. This measure usually correlates closely with cost. It is a component of Process Performance (do we have enough effort applied to accomplish the defined tasks).
|  |  | Staff Turnover Rates | The Staff Turnover Rates measure counts staff losses and gains versus plans. Excessive turnover impacts learning curves, productivity, and the ability of the supplier to implement the system with the resources provided within cost and schedule. This measure is most effective when used in conjunction with the Staff Experience measure. Loss of key and experienced personnel is critical.
Facilities and Support Resources
|  |  | Resource Availability | The Resource Availability measure tracks the availability of key development, test environment, and renewable resources. The measure is used to determine if key resources are available when needed. It can be integrated into the Milestone Dates measure. Personnel resources are not included in this measure (they are tracked with Effort or Staff Experience).
|  |  | Resource Utilization | The Resource Utilization measure counts the hours of resource time requested, allocated, scheduled, available (after maintenance downtime or other problems), and used. Resource Utilization is relevant to projects that have resource constraints and is usually focused only on key resources. This measure provides an indication of whether key resources are sufficient and if they are used effectively.
| Risk | Technical Risk
|  |  | Risk Status | The Risk Status measure counts the number of risks identified and the number that have mitigation plans. It may also count the number of risk mitigation plans that are funded, and the status of those risk mitigation plans. It can also be used to track the number of risks materialized and associated consequences (generally in dollars). It provides an indication of how well the project is identifying and addressing risks. It can provide an early indication of the probability of completing the project within cost and schedule constraints.
|  |  | Risk Exposure Trends | Risk Exposure Trends identify the overall risk exposure on a project over time. Risk exposure is defined as the likelihood of a risk times its consequences. It may be a point number, or described as a probability distribution over Risk Exposure Trends can be used to measure the aggregate amount of liability, to identify what indemnification is needed. Risk exposure trends may be delineated by those related to cost, schedule, or performance. | Mission critical and human critical exposure (limited subsystems that are human or mission critical can cause a catastrophic failure depending on where in the fault tree your responsibilities lie). Probability and actuality (realized). Risk insurance.
|  |  | Risk Treatment Trends | Risk Treatment Trends provide an indication of how successful a project is in mitigating risks. They can also be used to evaluate the budget for risk treatments, including the estimated budget, the amount actually spent, and the remaining amount of managing reserve for mitigating future risks. Risk treatment trends may be delineated by those related to cost, schedule, or performance.
Cost and Schedule Risk
|  |  | Schedule Impact Risk Trends | Schedule Impact Risk Trends identify the overall schedule risk on a project over time. They provide an indication of the differences between an original schedule estimate and current schedule estimate. They provide an indication of whether a project can be completed within the planned schedule. | Cost and Schedule risks are probability distributions for cost and schedule, respectively. They provide the probability that the cost or schedule respectively will exceed a desired target value.
|  |  | Cost Impact Risk Trends | Cost Impact Risk Trends identify the overall cost risk on a project over time. They provide an indication of whether a project can be completed within the planned budget. There are two costs: one due to the risk (if it is realized), and one due to the cost of implementing the risk mitigation plans. | Cost and Schedule risks are probability distributions for cost and schedule, respectively. They provide the probability that the cost or schedule respectively will exceed a desired target value.
Size and Stability
Physical Size and Stability
|  |  | System Element Trends | The System Element Trends measure describe the behavior of system elements over time. It quantifies the trends related to growth, change, completeness, and correctness of the definition of system elements. A system element may be defined as a discrete hardware and/or software portion of a system. This measure provides a way of assessing changes in the system's physical size as measured by its number of elements. It also provides a way to assess progress by analyzing completeness of the definitions, as well as their quality (correctness). System elements added, changed, and deleted may be reported by time period.
|  |  | Interface Complexity | The Interface Complexity measure quantifies the number and complexity of the information passing through the system interfaces, including both internal and external interfaces. This represents the amount and nature of the information passed between pairs of system elements. Interface Complexity may be presented by increment, system element boundary, nature of interface, type, etc. This measure also counts the number of interfaces that are added, modified, or deleted. Changes in the number of estimated and actual interfaces indicate risk due to requirements, architectural, or design volatility and may result in additional work. | This tracks can be used to track both physical and logical interfaces.
|  |  | Interface Compatibility | The Interface Compatibility measure quantifies the degree of conformance between the information sent and received between system elements. It provides an indication of interoperability across systems. The compatibility aspect measures the degree of compatibility between the sender and receiver sides of the information exchange. Interface Compatibility may be presented by increment, component boundary, nature of interface, type, etc. | This tracks can be used to track both physical and logical interfaces.
|  |  | Lines of Code Trends | The Lines of Code Trends measure reports the trends related to growth and change of the number of lines of code in the software part of the system. This measure may be used to depict the logical or physical size in lines of code. Lines of code added, changed, and deleted may also be reported. Lines of Code Trends may be presented by increment, source, language, delivery status, end-user environment, etc. This measure helps in estimating project cost, required effort, schedule, and productivity. It can also be used to normalize productivity measures and defect rates. Changes in the number of lines of code indicate development risk due to product size volatility, and possible additional work.
Functional Size and Stability
|  |  | Requirements Trends | The Requirements Trends measure quantifies the trends related to growth, change, completeness, and correctness of the definition of requirements. This measure may be used to depict the functional size in number of requirements by time period. This can be applied at any level, including capabilities, needs, stakeholder requirements, system requirements, interface requirements, system element requirements, or system functional applications. Requirements added, changed, and deleted may be reported. Requirements Trends may be presented by increment, change source, system element, priority, level, etc. Significant requirements changes, as indicated by this measure, provides an early warning of cost and schedule impacts, and potential rework.
|  |  | Architecture Element Trends | The Architecture Element Trends measure quantifies the trends related to growth, change, completeness, and correctness of the definition of the architecture elements. An architecture element may be defined as a basic building block of the selected architecture. Architecture elements added, changed, and deleted may be reported by time period. Architecture Element Trends describe the behavior of architecture elements over time. Significant architectural element changes, as indicated by this measure, provides an early warning of cost and schedule impacts, and potential rework.
|  |  | Functional Element Trends | The Functional Element Trends measure quantifies the trends related to growth, change, completeness, and correctness of the definition of the functional elements. A functional element may be defined as a basic building block of the functions or activities performed by the system. Functional elements added, changed, and deleted may be reported by time period. Functional Element Trends may be presented by subsystem, component, increment, function, etc. Functional Element Trends describe the behavior of functional elements over time. Significant functional element changes, as indicated by this measure, provides an early warning of cost and schedule impacts, and potential rework.
|  |  | Work Unit Backlog Size Trends | The Work Unit Backlog Size Trends measure quantifies the amount of unfinished work at any point in time. It is are useful for projecting the completion of particular activities or the project. It should be correlated with the sufficiency/capability of team resources. Work Units may be defined as base measures of unresolved defects (systems testing), open stakeholder problem reports, open service requests (services), story points or features not yet implemented (agile), open actions or assignments, or maintenance actions.
|  |  | Function Points Trends | The Function Points Trends measure reports the trends related to growth and change of the functional size of the software product as measured in function points (a weighted count of the number of external inputs and outputs, logical internal files and interfaces, and inquiries for a system). Function points added, changed, and deleted may be reported by time period. Function Point Trends may be presented by system element. Function Point Trends describe the behavior of function points over time. This measure determines the functional size of software to support an early estimate of the required level of effort. It can also be used to normalize productivity measures and defect rates.
|  |  | Call Center Request Trends | The Call Center Request Trends measure quantifies the trends related to number, type, severity, priority, and other relevant characteristics of the requests received by the call center. Requests can be categorized as problems or enhancements. Call Center Request Trends describe the behavior of call center requests over time. This measure provides information on product defects or usability problems encountered in the field. The number of discovered defects indicates the quality of the delivered product. The number of reported usability problems reflects the usability of the product design. Support request status (number open and closed) measures the ability of the supplier to support the product after delivery. Tracking the length of time that requests remain unresolved can determine the level of customer satisfaction achieved by the product support activity. | Each request’s priority is proposed by the customer and assigned by the support activity, based on an assessment of the problem’s impact on both the acquirer and supplier
|  |  | TBR/TBD Trends | The TBD/TBR trends measures the amount of work that has been deferred. These measures provide an indication of the level of technical risk in the project, due to the uncertainty of the required work to be performed. They provide an early warning of potential rework, with associated cost and schedule impacts. | TBR=To Be Resolved TBD=To Be Determined This measure needs to be consistently applied to the same element, e.g. TBDs for requirements, and not mixed, e.g. TBDs on requirements or on action items. Different element have very different level of uncertainty.
| Product Quality | Functional Correctness
|  |  | Defect Profiles | The Defect Profiles measure quantifies the number, status, and priority of defects reported and resolved. It provides useful information on the ability of a supplier to find and resolve defects in hardware, software or documentation. The number of defects indicates the amount of rework, and has a direct impact on quality. Arrival rates can indicate product maturity (a decrease should occur as testing is completed). Closure rates are an indication of progress, and can be used to predict test completion. Tracking the length of time that defects have remained open can be used to determine whether progress is being made in fixing defects, or whether rework is being deferred.
|  |  | Defect Density | The Defect Density measure is an expression of the number of defects relative to the size of a product. Defect Density measures can identify system elements with the highest concentration of defects, which might be candidates for additional testing or for redesign/rework.
|  |  | Technical Measurement Trends | The Technical Performance measure is a combination of other measures that are defined by the system’s functional and technical requirements. These measures address any functional characteristics that can be quantitatively defined and demonstrated. Various types of functional requirements may be measured including user and mission functions, interoperability of components, security features, accuracy of the system component functions, response time, data handling capability, or signal processing. These measures provide an indication of the overall ability of a system to meet the users’ functional requirements.
|  |  | System Elements Accepted | The System Elements Accepted measure quantifies the number of system elements accepted against defined criteria by system test or ultimately the customer. This is evaluated against the plan for when system elements are expected to be accepted. It provides an indication of system quality, and an evaluation of when a system will be completed.
Supportability - Maintainability
|  |  | Time to Restore | The Time to Restore measure quantifies the time to recover from a system failure. Restoring the system may include two tasks: immediate restoration of operational capability and fixing the root cause of the problem (see time to repair). A comprehensive measure includes the elapsed time, effort, and resources needed for system restoration and for problem resolution. This information supports trade-offs between system design and integrated logistics support characteristics. Historical data is used during system design to evaluate alternative solutions to optimize the time to restore system operation. Time to Restore measures are used for integrated logistics support planning to determine adequate maintenance methods that will ensure operational availability.
|  |  | Mean-Time-to-Repair | The Mean time to repair (MTTR) measure quantifies the average time required to repair a failed system element or device. It is a indication of the maintainability of repairable items. Expressed mathematically, it is the total corrective maintenance time divided by the total number of corrective maintenance actions during a given period of time. Although it can be used at any stage of a product development, it is often part of a maintenance contract, where it is an element to determine Operational Availability. For instance, a MTTR of 24 hours is much better and usually more costly than one of 7 days.
|  |  | Cyclomatic Complexity | The Cyclomatic Complexity measure is usually applied to count the number of unique logical paths in a software system element. However, the concept of Cyclomatic Complexity also can be used to evaluate the complexity of control or information flow in a system. This measure provides an indication of both design quality and the amount of testing required. A high complexity rating is often a leading indicator of a high defect rate. System elements with high complexity usually require additional reviews, increased testing, or rewriting. Other component-complexity measures include essential, Halstead, and data flow complexity. | Discuss coupling measures as options (in spec)
Efficiency
|  |  | Utilization | The Utilization measure quantifies the portion of a system element resource available, allocated and/or used during specific system operational modes. A system element resource might include CPU, I/O, memory, or storage. Specific to the quantification of the allocated or available resources is the method of quantification (i.e.. estimated, modeled, or measured). This measure indicates whether the specified resources are sufficient to meet the operational requirements or conversely whether the operational requirements are suitable to be implemented in the allocated or available resources.
|  |  | Throughput | The Throughput measure provides an estimated or actual value for flow of materials or information (such as processing or data transfer) during a specified period of time. The measure indicates whether the system element or system can support its operational requirements. The measure also provides a basis to determine if future enhancement requirements and technology upgrades can be accommodated.
|  |  | Response Time | The Response Time measure quantifies the portion of a response time-line available, allocated and/or used during specific system operational modes. The measure reports the amount of time required to perform a function, such as task completion or request processing. The measure counts the time between initiation and conclusion of an event, such as a request for service. Specific to the quantification of the response time is the method of quantification (i.e.. estimated, modeled, or measured). This measure indicates whether the allocated response times are sufficient to meet the operational requirements or conversely whether the operational requirements are suitable to be implemented in the allocated response time.
Portability
|  |  | Interface compliance | The Interface compliance measure quantifies the compliance to the interface specification (number of services, data fields), and provides an indication of interoperability. It may be evaluated by evaluation, project test (testing of interfaces may be detailed in the test procedures), or interoperability testing.
Usability
|  |  | User Interface Acceptability | The User Interface Acceptability measure provides an indication of user acceptance of the system. It is often evaluated through user evaluation or HMI Testing. Examples include pilot simulations of cockpit, and level of negative comments received during demos/piloting.
|  |  | Operator Errors | The Operator Errors measure quantifies ease of use and system reliability in the operational environment. This measure provides insight into system failures or anomalies attributed to operational causes rather than to hardware or software discrepancies.
Dependability - Reliability
|  |  | Mean-Time-to-Failure (MTTF) | The Mean-Time-To-Failures (MTTF) measure provides an indication of reliability of a non-repairable system or component. MTTR is calculated as the system or element operating time until a failure occurs.
|  |  | Availability | Availability of a system is measured as the “up” time in which the system can perform its mission, divided by the total time during which the system is expected to perform the mission. "Down" time should include both corrective and preventive maintenance times. This measure provides an indication of operational availability, and the suitability of the system for operational use. | Availability can be calculated as MTBF divided by MTBF plus MTTR (both corrective and preventive maintenance times).
Security - Safety
|  |  | Profile of Vulnerabilities | The Profile of Vulnerabilities measure looks at how many defects of a particular type are identified and corrected over the life cycle of the program. In particular security defects in the specific categories can be tracked for trends, with Category 1 being the most severe. Measures in this category can address the cost and impacts of attacks realized, or how many attacks were attempted and successful. These measures provide an indication of the security of the system. | DISA vulnerability categories: - Category I: Vulnerabilities that allow an attacker immediate access into a machine, allow super user access, or bypass a firewall. - Category II: Vulnerabilities that provide information that have a high potential of giving access to an intruder. - Category III: Vulnerabilities that provide information that potentially could lead to compromise. - Category IV: Vulnerabilities that, when resolved, will prevent the possibility of degraded security.
|  |  | Cost to Fix Vulnerabilities | The Cost to Fix Vulnerabilities measure quantifies the cost to fix security defects and vulnerabilities.
|  |  | Attack Pattern Test Coverage | The Attack Pattern Test Coverage measure evaluates whether all known attack patterns have been tested. This provides an indication of they security of the system.
| Process Performance | Process Compliance |  |  | Indicators from other information categories can also be analyzed for process performance. See Schedule and Progress (Indicators from Work Unit Progress and Work Backlog concepts). See Resources and Cost (Financial Performance and Personnel Effort concepts). See Size and Stability (Physical Size and Stability and Functional Size and Stability concepts). See Product Quality (Functional Correctness, Supportability - Maintainability).
|  |  | Process Reference Maturity/Capability Model Rating | The Process Reference Model Rating measure is generally done at the enterprise level, but can be applied for a large project (see enterprise definition). A typical process model used is the CMMI. At the project level, the measure focuses on where an individual project complies with enterprise processes, and where tailoring (changes) were required. Some examples reflecting the use of the process can include: Counting the number of tailorings over time: counting the number of approved M&A plans or measurement reports reviewed over time.
|  |  | Process Audit Findings Distribution | The Process Audit Findings Distribution measure indicates how well the project is following the process defined by the enterprise. It provides insight into coverage of audit areas, ensuring compliance with the organizational processes and providing process audit schedule visibility. This measure counts the number of defined process elements (often documented in a checklist) that were reviewed and the number that pass the audit. Generally, passing an audit means that the enterprise actually follows the procedures that are defined for that process element. The ratio of these numbers provides information on the level of compliance achieved in each audited process elements. This measure may also indicate which specific process elements need corrective action.
Process Efficiency
|  |  | Productivity Performance Trends | The Productivity Performance Trends measure provides a ratio of the amount of product completed to the amount of effort expended. This measure is a basic input to project planning and can evaluate whether performance levels are sufficient to meet cost and schedule estimates. Productivity is also useful early in the project for estimate and baseline comparisons before actual productivity data is available.
|  |  | Cycle Time Performance Trends | Cycle Time Performance Trends measures provide a comparison of schedule times against organization norms, for specific activities, processes, or projects. Measures evaluate current status and whether process improvements are effective. Measures could include a comparison of actual versus expected durations for defined tasks within the process.
|  |  | Service Level Agreement (SLA) Response Trends | Service Level Agreement (SLA) Response Trends measure how the support function is working with the customer. They evaluate whether the criteria established in the SLA are being met.
Process Effectiveness
|  |  | Defect Containment | The Defect Containment measure identifies defects that were inserted and caught within a process or phase, or its corresponding review activity. This allows a calculation of those that "escaped" or where caught in a later phase or process (also sometimes called "Defect Escapes"). This measure indicates how well the review and verification processes are performing. The amount of defect containment is related to the amount of effort, resources and tools applied.
|  |  | Test Effectiveness | The Test Effectiveness measure indicates the capability of the testing process. It measures the filtering capability of the test to detect defects in each testing phase: unit test, functional test, system test, etc. The test effectiveness is a ratio between the number of defects that were detected in a specific testing phase over the total number of faults that are actually in the product under test. However, the actual number of remaining defects is never known. Historical data may help to predict the number of remaining defects that could slip to next testing phases.
|  |  | Test Coverage | Test coverage measures how much a system has been exercised by tests. It helps assess how many times a particular function, system element, or test condition has been executed or if it has ever been executed. In software testing, this measures if all statements in a program have been executed, at least once. Test coverage can be used to determine if there are test procedures missing to complete 100% test coverage. This measure provides confidence that the system will perform as expected.
|  |  | Defect-Prone System Elements Distribution | The Defect-Prone System Elements Distribution measure tracks the amount of defects detected in each system element and identifies those system elements that most need to be improved. It is especially relevant for key elements of the architecture and those that directly affect the Operational Availability of the system. It can also be used to improve the performance of the processes by identifying root causes of defect-prone development phases.
|  |  | Operational and Maintenance Effectiveness | Operational and Maintenance Effectiveness measures provide an evaluation of how effective the organization is at delivering solutions to the problems reported by the customer. Measures track the number of critical defects that have been resolved against the number that have been identified over time.
|  |  | Rework Effort Distribution | The Rework measure tracks the amount of work effort expended to fix defects, compared to the rework budget and the total effort. Rework may be expended to fix any product. This measure identifies the quality of the initial project effort, products that need the most rework, and processes that need improvement. Budgets should be estimated for rework in each phase.
|  |  | Rework System Elements Trends | The Rework System Element Trends measure quantifies the number of system elements that require rework. System elements added, changed, and deleted may be reported by time period. The focus is on systematic root cause analysis that focuses on which system elements need to be redesigned or reimplemented.
| Technology Effectiveness | Technology Suitability
|  |  | Requirements Coverage | The Requirements Coverage measure quantifies the amount of functionality that can be addressed by a specific technology or off-the-shelf component (COTS, GOTS, NDI, or reuse). This measure can also determine whether a candidate technology can provide the required functionality.
Technology Maturity
|  |  | Technology Maturity Trends | The Technology Maturity Trends measure quantifies the trends related to changes in technology maturity. Technology maturity describes the stability of a technology and its susceptibility to obsolescence. Technology Maturity Trends describe the behavior of technology maturity over time.
Technology Volatility
|  |  | Technology Baseline Changes Trends | The Technology Baseline Changes measure monitors the number of times a technology changes over time. The rate at which a technology evolves can indicate the stability of the underlying technology or the stability of the product implementing that technology. This measure assesses the risk of incorporating unfamiliar technology into a project or system. In particular, it provides one view of the frequency at which the technology is likely to change. Information from this measure can help determine when to adopt a technology.
| Customer Satisfaction | Customer Feedback
|  |  | Satisfaction Ratings Trends | Satisfaction Ratings Trends indicates the change, over time, of customer satisfaction with a delivered system or with a project team’s performance. The customer scores a system or the project team’s performance with respect to pre-defined evaluation criteria and using a quantitative scale. Performance ratings are generally collected via surveys or interviews. They can be used to collect data from acquirers, customers and users.
|  |  | Award Fee Distributions | Award Fee Distributions measures track compensations received from the acquirer as a result of meeting contractually specified award fee criteria, for example, due to good quality, good performance, services effectiveness, on-time and within-budget delivery, etc.. It is usually expressed as a dollar amount, representing the value of the award fee.
Customer Support
|  |  | Support Request Distributions | The Support Request Distributions quantifies the number of support requests that are received and addressed over time. It could relate to a larger customer base or to issues with product quality. Increases in the number of support request equates to longer wait time for support which reduces customer satisfaction. | This impacts the resources and support time required for support.
|  |  | Support Time Trends | The Support Time Trends measure quantifies the trends related to changes in the time required to respond, resolve, or satisfy an acquirer's request for support, against the goal. Average time to respond, average time to resolve, maximum time to respond and maximum time to resolve may be reported by time period, along with other quantities of interest.
Enterprise
Schedule & Progress
Milestone Completion
|  |  | Enterprise Milestone Status | The Enterprise Milestone Status measure indicates progress made with respect to significant milestones and, as applicable, interim milestones. Status provided by projects are analyzed individually and then consolidated into status reports for each category of project (e.g., engineering projects, IT purchases and installations, space planning activities, studies). The milestones that are collected from each project should be consistent (e.g. funded, awarded, delivered to test, fielded). | Milestone Status reported to the enterprise by the projects should include (a) schedule milestone performance (on target, time behind, time ahead), (b) satisfaction of criteria for earning schedule credit OR whether criteria were waived and if so, why, (c) evidence used to validate criteria were satisfied.
Work Backlog
|  |  | Work Unit Backlog Trends | This measure tracks trends in the number of work units, over time, to help assess the quantity of work remaining across the enterprise. This could be service requests, maintenance actions, open defects or open stakeholder problem reports, or functional changes. It can be used to evaluate the capacity that is needed by an enterprise. It is most applicable at an enterprise with a large set of smaller projects, service organizations, or IT projects.
|  |  | Burndown Rates | The burndown rate measure indicates the "velocity" of an enterprise to finish the tasks or systems planned for a certain period. It can be used to assess how an enterprise is doing toward meeting their goals.
Resources & Cost
Financial Performance
|  |  | Funding Availability | The Funding Availability measure tracks the budgets requested versus received. it provides an indication of the financial health of an enterprise, and the number of unfunded priority initiatives. For small companies, the focus is often as doing as much as you can with the money you have . | Track funding for categories such as system development, research, administrative, overhead, etc.
|  |  | Disbursement / Obligation Rate Trends | The Disbursement / Obligation Rate Trends measure looks at the amount of money received and spent over time. It is used to evaluate whether spending is occurring at the correct rate. It is important for small businesses (to evaluate whether the money is coming in or going out as it is supposed to) and for government (to ensure all expected funding is received and that moneys provided are spent before the money expires).
|  |  | Earnings Progress | The Earnings Progress measure looks at the amount of earnings received over time. This is especially important for commercial companies. Companies track receivables and also track contributions to the bottom line.
|  |  | Return on Investment Capital | Return on Investment (ROI) Capital measures whether investments achieve their expected ROI. May be used to evaluate how long it takes to reach break even point for business cases.
Personnel Effort
|  |  | Staff Level Sufficiency | The Staff Level Sufficiency measure determines an enterprise's skill level and experience level with respect to a defined area or domain, against the enterprise needs, both now and projected into the future. This measure can also address the quantity of training and years of experience in a particular domain or subject matter. Data may be evaluated by depth of expertise (Novice, Apprentice, Journeyman, Master, etc.). At t he enterprise level, this measure may also include non-project personnel.
|  |  | Effort Distribution and Trends | The Effort Distribution and Trends measure counts the number of labor hours or number of personnel applied to all project against the enterprise total counts. It provides an indication of whether the enterprise is overstaffed or understaffed. These measures are focused on balancing personnel needs of multiple projects across each project's peaks and valleys. It provides a guide to evaluating the capability of the enterprise to enter new areas and address new technologies.
|  |  | Workforce Skills Profiles | Workforce Skills Profiles are used to evaluate the balance of competencies across an enterprise. This includes assessing skill needed for innovation and future needs.
|  |  | Workforce Age Profiles | Workforce Age Profiles are used to evaluate and balance the experience levels across the organization. They are useful for succession planning, and help to determine where training and skill transition to less experienced personnel are needed.
|  |  | Staff Turnover Rates | The Staff Turnover Rates measure counts staff losses and gains versus plans. Excessive turnover impacts learning curves, productivity, and the ability of the supplier to deliver and maintain systems. Loss of key and experienced personnel is critical. High turnover rates are usually indicative of major problems: the enterprise needs to understand the causes of turnover.
Facilities and Support Resources
|  |  | Resource availability | Resource Availability measures indicate, for a given key enterprise resource, whether enough, too much, or not enough of a resource exists. This measure assists in investment and retirement decisions for enterprise resources. It should assess not only current resource needs, but also projected future needs. It is used to assess facilities management issues such as: what should be modernized, what is being used today, where new capacity is needed, where to spend update money | Key data collection and analysis activities include: (1) identify the resources to be measured, (2) define appropriate uses/eligible users, (3) use a scheduling mechanism to assess "booked" time vs. "used" time and reallocate/reshuffle as needed, (4) use "request" mechanism to log requests and then analyze data to determine whether more of a resource needs to be procured to reduce schedule/productivity issues related to waiting time, or if a resource can be retired.
|  |  | Resource utilization | The Resource Utilization measure counts the hours of resource time requested, allocated, scheduled, available (after maintenance downtime or other problems), and used, for key enterprise resources (this is often major facilities or those with limited capacity). This measure provides an indication of whether key resources are sufficient and if they are used effectively.
Risk
Technical Risk
|  |  | Portfolio Risk Status | At the enterprise level, the Risk Status measure focused on risks that cross project boundaries, or affect the enterprise as a while. It is a measure of the number of risks identified and the number that have mitigation plans. It can also be used to track the number of risks materialized and associated consequences (generally in dollars). It provides an indication of how well the enterprise is identifying and addressing risks. It can be used balance the risks across portfolios of projects. It can also be used to identify systemic risks or trends, that could affect future projects.
|  |  | Risk Tolerance | The Risk Tolerance measure assesses the willingness of an enterprise to support risk. Higher risk generally has higher potential for reward.
Cost and Schedule Risk
|  |  | Schedule Impact Risk Profile | At the enterprise level, Schedule Impact Risk Trends identify the overall schedule risk across the enterprise, or a portfolio of projects. They can provide information on balancing schedule risks across the portfolio or enterprise by illustrating the balance at each point in time.
|  |  | Cost Impact Risk Profile | At the enterprise level, Cost Impact Risk Trends identify the overall cost risk across the enterprise, or a portfolio of projects. They can provide information on balancing costs risks across the portfolio or enterprise by illustrating the balance at each point in time.
Size & Stability
Physical Size and Stability Functional Size and Stability
|  |  | Platform/System Trends | The Platform/System Trends measure quantifies the installed application baseline (e.g. system elements (components), lines of code, function points) of an enterprise. It evaluates systems in development, maintenance, operations. This measure provides an indication of the total application base, and how that is changing over time.
|  |  | External and Cross-Platform Interface Complexity | The External and Cross-Platform Interface Complexity measure quantifies the number and complexity of the information passing either externally, or across systems. This represents the amount and nature of the information passed between systems. It provides an indication of the complexity across systems. | Need to define how this will be measured.
|  |  | External and Cross-Platform Interface Compatibility | The External and Cross-Platform Interface Compatibility measure quantifies the degree of conformance between the information sent and received between systems, of those passing either externally, or across systems. It measures the degree of compatibility between the sender and receiver sides of the information exchange. It provides an indication of interoperability across systems.
Product Quality
Functional Correctness Dependability-Reliability
|  |  | Stakeholder Defects Distribution | The Stakeholder Defects Distribution measure quantifies the number, status, and priority of defects reported by the stakeholder, after fielding. The number of defects indicates the amount of rework, and has a direct impact on customer satisfaction. Tracking the length of time that defects have remained open can be used to determine whether progress is being made in fixing defects, or whether rework is being deferred.
|  |  | Warranty Trends | The Warranty Trends measure tracks the amount money spent on warranties. Warranty trends impact the balance sheet bottom line.
Process Performance
Process Compliance
|  |  | Reference Maturity/Capability Profile | The Process Reference Model Rating measure compares the implementation of the enterprise's defined process with the requirements of an accepted reference model. The rating results from an assessment of the enterprises' process capabilities. A published process model guides the assessment. With the reference model rating and assessment findings, the organization can identify opportunities for improving processes and can measure progress. This measure is sometimes used during contract source selection to evaluate competing suppliers. Staged-view process models provide a single overall rating for organizational process maturity and a profile of the achieved process components. Continuous-view process models provide a capability rating for each process component that is assessed (rather than a single enterprise rating). The quantitative measurement results are limited to the date of the assessment or evaluation and the awarded rating level. However, the most useful assessment information is qualitative, including strengths and weaknesses of technical and management capabilities that are key to an organization’s or project’s success.
|  |  | Process Audit Findings Distribution | The Process Audit Findings Distribution measure indicates how well the set of projects is following the enterprise processes. It provides insight into coverage of audit areas, ensuring compliance with the organizational processes. This measure may also indicate which specific process elements need corrective action.
|  |  | Exception Distributions | The Exception Distributions measures identifies those assets of a process asset library that have the most exceptions/waivers against them. These are often good candidates for leaning, process improvements, etc.
Process Efficiency
|  |  | Productivity Baselines and Trends | Productivity Baselines and Trends measures provide a summary description of the productivity of an enterprise over time. It provides a view of the productivity of an enterprise, defined as some central value (mean, median, weighted mean, etc.) obtained from its projects. These provide a baseline for developing project estimates, and for evaluating project performance.
|  |  | Cycle Time Baselines and Trends | Cycle Time Baselines and Trends establish enterprise norms for length of time that it takes a process to complete all associated activities. The accumulation of all processes determines the total schedule to complete a project. Usually, a key objective in process improvement is to reduce cycle time of a project, or of specific activities.
Process Effectiveness
|  |  | Rework Effort Distribution | The Rework measure tracks the amount of work effort expended to fix defects across the enterprise. The focus is on where processes need to be improved, and systemic root cause analysis.
Technology Effectiveness
Technology Maturity
|  |  | Technology investment versus plan | Technology investment versus plan looks at innovation and whether an enterprise is developing technology to meet new needs. The measures evaluates whether an enterprise is targeting the right areas, and whether the enterprise is getting the expected results.
|  |  | Needs Met by Technology | Needs Met by Technology looks at whether an enterprise's investments in technology are meeting needs. The measures evaluates whether an enterprise is getting expected results.
Customer Satisfaction
Customer Feedback
|  |  | Satisfaction Ratings Trends | Satisfaction Ratings Trends indicates the change, over time, of customer satisfaction with an enterprise, across a set of projects . The customer scores an enterprise with respect to pre-defined evaluation criteria and using a quantitative scale. Performance ratings are generally collected via surveys or interviews. They can be used to collect data from both acquirers, customers, and users.
|  |  | Market Share | Measures of market share evaluate an enterprise's share (e.g., in dollar volume of sales or volume of goods sold) of a business area. They are used to assess dominance in a market, and to support decision-making on areas to improve, expand, or branch out. The strongest indicator of Customer Feedback is purchasing the organization's product, so monitoring how the organization is performing against its peers is critical. This is a relative measure, so it measures how the organization keeps up with trends and responds effectively to its environment. | Market share is generally not an issue for government or non-profit enterprises. Those enterprises tend to be concerned with mission accomplishment, Value for Money or Return on Investment.
Note on D2: Indicators are often trends over time of planned versus actual values. They might also be represented as rates, status as of one date, comparisons between attributes or entities, or other relationships.