## Information Need
Role: | Possible Information Needs:
Employee | Should I update my resume?
Employee | Go back to school?
PM | As a PM, what can I do to improve the chances of my project delivering on schedule?
PM | Meeting this year's budget and schedule goals?
PM | How much more money (or time) is needed to reach IOC (Initial Operating Capability)?
Support Organization | Is our organization increasing the executability of the projects we support?
Funding Allocator | Is a second supplier needed for product X?

## Sample IOC indicator
Function | Actual % Complete | Planned % Complete
Security | 10 | 30
Reports | 35 | 70
Function A | 85 | 100
Function B | 70 | 87
Infrastructure | 87 | 85
Data Migration | 15 | 60
Average | 50.3333 | 72

## Open Defect Trends
Date | Open Defects
2009-07-01 | 50
2009-08-01 | 60
2009-09-01 | 70
2009-10-01 | 80
2009-11-01 | 90
2009-12-01 | 110
2010-01-01 | 140
2010-02-01 | 135
2010-03-01 | 115
2010-04-01 | 105
2010-05-01 | 108
2010-06-01 | 110