## ICM Table
AGILE Information Category-Measureable Concept-Prospective Measures
| Information Categories | Measurable Concepts | Questions Addressed | Measures |  | Notes
|  |  |  | Prospective Indicators | Sample Base Measures
Team Measures | Schedule and Progress | Milestone Completion (time box progress only) | Are the iterations completing as scheduled? | Iterations Completed | - Cycle Time by iteration | - Most agile projects have standard iteration durations. Continued changes to the duration time indicate problems with completing committed stories per plan
|  | Work Unit Progress | Are specific stories completed as scheduled for that iteration? | - Iteration Burn-Down - Committed vs Delivered Stories - Test Case Progress | - Stories Committed, Delivered, Accepted - Problem reports Discovered, Closed - Test cases Automated, Attempted, Passed | - Problem reports may be converted to stories
|  | Work Backlog | Will all of the planned Stories be delivered for this iteration, or will stories need to be Deferred (or added)? How many stories remain in the Working Backlog for the next iteration? How many stories are deferred ? | - Backlog Trends - Burndown Rates - Deferred stories | - Stories in backlog over time | - The product backlog contains a prioritized list of the Stories desired by the customer, and represents the potential scope of the program.
|  | Incremental Capability | Are stories being delivered in increments as scheduled. | - Story Points Delivered vs Planned |  | - This is a cumulative look at the stories accepted/delivered from the Work Unit Progress Measure.
| Resources and Cost | Financial Performance | Is the iteration meeting budget objectives? | - Cost Trends | - Budget, planned, and actual costs
|  | Effort/Staffing | Are iteration teams staffed with the correct mix of skills and capabilities? Is there turnover ? Are Subject Matter Experts available to support this effort? | - Staff Level Sufficiency - Effort Distribution and Trends - Team Stability - SME availability | - Number of staff by skill level on project and projected - Staff added, removed, quit | - The data for an agile staffing profile is identical to data used for a traditional staffing profile. However, the expected shape of the staffing curve is significantly different for an agile program. In general, the curve should be much flatter for agile programs than for traditional programs since the short sprints require all discipline skills for most of the program duration. - Agile teams work closely together, and changes to team composition may significantly impact team performance for one or more sprints. If team velocity changes, the team stability measurement should be examined to see if that is a contributing factor.
|  | Facilities and Support Resources | Are needed facilities, equipment, tools, and materials available as needed to meet milestones? | - Resource availability - Resource utilization | - Quantity needed, available - Time required, available, used
| Size and Stability | Physical Size and Stability | How many interfaces exist for the product? | - External Interface Trends | - Interfaces identified developed and verified
|  | Functional Size and Stability | How big is the product? How much change is occurring? | - Story Point Trends | - Story Points Committed vs. Delivered - Iteration Burndown | - In general, the number of changes to each product, or each set of related products, should peak following the initial demonstration of capability and then decrease in each following sprint. Excessive changes over time may have several causes including thrashing, inadequate architecture partitioning, lack of domain knowledge, or lack of timely user participation in reviews.
| Product Quality | Functional Correctness | Is the product good enough for user demos? Are identified problems being resolved? | - Defect Escapes - Defect Rework - Technical Measurement Trends - Story Points Accepted | - Defects by priority - Technical measurement requirement, target, threshold, budget, and actual - Story points verified | - Technical measurement includes Measures of Effectiveness, Measures of Performance, and Technical Performance Measures - Identified Defects may be converted to stories which creates rework
Supportability - Maintainability
|  | Efficiency | Does the target system still meet response time requirements as the functionality is added and the system is scaled to full implementation. | - Response Time | - Time for function (budget, actual) | - It is important to capture benchmark times for key system functions. These can be reviewed as the system is maintained or altered, to ensure that no degradation occurs.
Portability
|  | Usability | Is usability maintained through iterations/releases?
|  | Dependability - Reliability | Is dependability reliability maintained through iterations / releases?
|  | Security - Safety | Is security maintained through iterations / releases?
| Process Performance | Process Compliance
|  | Process Efficiency | Are the processes efficient enough to meet current commitments and planned objectives? | - Team Velocity | - Stories - Effort expended - Iteration duration
|  | Process Effectiveness | How much rework is occurring? | - Defect Containment - Automated Test Coverage - Rework Story Points | - Defect Escapes - Tests automated - Story Points related to rework
| Technology Effectiveness | Technology Suitability | Did the technologies selected continue to meet the needs as additional iterations and releases are completed? |  |  | May allocate story points to account for completion of technology insertion.
Technology Maturity
|  | Technology Volatility | How volatile is the technology used, including commercial products? | - Technology Story Point Trends | Number of story points impacted by changed technology | How often do the COTS versions, vendors, and capabilities change?
| Customer Satisfaction | Customer Feedback | How do our customers perceive our performance for individual projects and the enterprise? Are we meeting user expectations? | - Customer Feedback Story Points | Story points added due to customer feedback
|  | Customer Support | How quickly are customer support requests being addressed? | - Customer Feedback Story Points addressed | - Customer Feedback Story Points committed - Customer Feedback Story Points delivered
| Information Categories | Measurable Concepts | Questions Addressed | Measures |  | Notes
|  |  |  | Prospective Indicators | Sample Base Measures
Product Measures | Schedule and Progress | Milestone Completion | Are the releases completing as scheduled? | Releases Completed | - Cycle time by release | - Most agile projects have standard release durations. Continued changes to the delivery time indicate problems with completing commitments.
|  | Work Unit Progress | Are specific work units (iterations, capabilities, features, stories, problem reports) completed as scheduled? | - Release Burn-Down - Committed vs Delivered Work Units - Test Case Progress | - Work Units Committed, Delivered, Accepted - Problem reports Discovered, Closed - Test cases Automated, Attempted, Passed | - Problem reports may be converted to stories
|  | Work Backlog | Will all of the planned Capabilities / Features / Stories be delivered for this Release or will need to be Deferred (or added)? How many will remain in the Working Backlog for the next release How many are deferred ? | - Backlog Trends - Burndown Rates - Deferred work units | - Capabilities/Features/Stories in backlog over time | - The product backlog contains a prioritized list of the Capabilities/Features/Stories desired by the customer, and represents the potential scope of the program.
|  | Incremental Capability | Are Capabilities / Features / Stories being delivered in releases as scheduled. | - Work Units Delivered vs Planned |  | - This is a cumulative look at the Capabilities / Features / Stories accepted/delivered
| Resources and Cost | Financial Performance | Is the project or release meeting budget and schedule objectives? | - Budget Adequacy and Trends - Cost Trends - Cost and Schedule Impact Risk Trends | - Budget, planned, and actual costs - Cost and schedule risk | - For deployed systems, costs include those to operate, maintain (resolve problems), and enhance system - Include updates as funding changes - For risks, develop a range of cost values with associated probabilities, not just a single "cost" value, to facilitate improved awareness of potential cost exposure. Note that this should be related to both cost and schedule risk.
|  | Effort/Staffing | Is effort being expended according to plan? Are there sufficient iteration teams staffed with the correct mix of skills and capabilities? Is there turnover ? Are Subject Matter Experts available to support this effort? | - Staff Level Sufficiency - Effort Distribution and Trends - Skill Profiles - Effort Stability - SME availability | - Number of staff on project and projected - Number of staff by skill level - Staff added, removed, quit
|  | Facilities and Support Resources | Are needed facilities, equipment, tools, and materials available as needed to meet milestones? | - Resource availability - Resource utilization | - Quantity needed, available - Time required, available, used
| Size and Stability | Physical Size and Stability | How many interfaces exist for the product and are these stable? | - External Interface Trends | - Interfaces identified developed and verified - Interface changes
|  | Functional Size and Stability | How big is the product? How much change is occurring? | - Capabitities / Features / Stories Trends | - Number Committed vs. Delivered - Release Burndown
| Product Quality | Functional Correctness | Is the product good enough for delivery to the user? Are identified problems being resolved? How many problems are reported from the field? Does the product meet its technical measurement requirements? | - Defect Profiles - Defect Density - Incident Reports - Technical Measurement Trends | - Defects by priority - Incident Report Trends - Technical measurement requirement, target, threshold, budget, and actual | Technical measurement includes Measures of Effectiveness, Measures of Performance, and Technical Performance Measures
|  | Supportability - Maintainability | How much support does the system require? How difficult is it to support? | - Time to Restore - Mean-Time-to-Repair - Cyclomatic Complexity | - Hours to restore - Calendar hours and labor hours to repair - Number of paths through system | Support includes maintenance, training, provision of supplies, etc.
|  | Efficiency | Does the target system make efficient use of system resources? | - Utilization - Throughput - Response Time | - System element capacity available, used - Time for function (budget, actual) | It is important to capture benchmark times for key system functions. These can be reviewed as the system is maintained or altered, to ensure that no degradation occurs.
|  | Portability | To what extent can the functionality be re-hosted on different platforms? | - Interface Compliance | - Interfaces verified | Use of portability can also include reusability and adaptability
|  | Usability | Is the user interface adequate and appropriate for operations? Are operator errors within acceptable bounds? | - User Interface Acceptability - Operator Error Trends | - Actions from user interface reviews - Operator errors
|  | Dependability - Reliability | How often is service to users interrupted? Are failure rates within acceptable bounds? | - Mean-Time-to-Failure - Availability | - System element failures by severity, priority - System element start, end times | Instead of availability, might measure downtime (outages)
|  | Security - Safety | How many vulnerabilities are identified and remediated by life-cycle phase? How many relevant attack patterns have been covered by test cases? | - Profile of vulnerabilities - Cost to fix vulnerabilities - Attack Pattern Test Coverage Profile | - Vulnerabilities discovered, remediated - Cost to fix vulnerabilities - Test cases developed, verified per attack pattern
| Process Performance | Process Compliance | How consistently does the project implement the defined project and enterprise processes? | - Process Reference Maturity/Capability Rating - Process Audit Findings Distribution | - Maturity/Capability Rating Goal, Assessed - Number of audit findings by process area
|  | Process Efficiency | Are the processes efficient enough to meet current commitments and planned objectives? | Agile Efficiency Trends | story points per FTE per iteration - | For agile developments, team velocity is a measure of productivity Sprint durations are fixed
|  | Process Effectiveness | Are the processes generating the results expected? How much rework is occurring? | - Defect Containment - Test Effectiveness - Test Coverage - Defect-prone system elements distribution - Operational and Maintenance Effectiveness - Rework Effort Distribution - Rework System Elements Trends - Risk Handling Trends -Rework Story Points | - Defects by phase injected, discovered, and resolved (defect propagation) - Defects discovered per test case and test type - Defects discovered per system element - Schedule and effort expended - total and rework - System elements requiring rework - Number of identified risks treated per plan | - Defect containment is also called "Defect Escapes" - Defects per system element is particularly important for key elements of the architecture, or if safety/security related - For services, schedule and effort expended might include those related to service calls - Rework in production might measure waste of production units - Could also measure benefits of processes (e.g. cost prevention) - Risk trends may include overdue actions, age of open risk actions by severity or state Rework measurements measure the amount of stories that are put into Rework after the story is passed to IV&T, but before it is accepted at the CPR. This is an indicator on how well the story was written.
| Technology Effectiveness | Technology Suitability | Can technology meet all allocated requirements, or will additional technology be needed? | - Requirements Coverage | - Requirements met by technology
|  | Technology Maturity | Is the technology ready to be used in this project? Does the technology risk impact the achievement of planned objectives? | - Technology Maturity Trends - Risk Exposure Trends | - Technology Readiness Level (TRL) - Number risks identified, treated, closed by probability and consequence | - Might also consider technology obsolescence - is the technology about to become obsolete? - Technology risk may also be seen in technology volatility - Risk identification may be by priority - Risk handling may include analysis, approval, implementation, verification, and closure
|  | Technology Volatility | Does new technology pose a risk due to too many changes? | - Technology Baseline Changes Trends | - Number of requirements impacted by changed technology
| Customer Satisfaction | Customer Feedback | How do our customers perceive our performance for individual projects and the enterprise? Are we meeting user expectations? | - Satisfaction Ratings Trends - Award Fee Distributions | - Satisfaction ratings - Award fees received | Contractor Performance Assessment or other survey
|  | Customer Support | How quickly are customer support requests being addressed? | - Support Request Distributions - Support Time Trends | - Number of support requests - Calendar time to address requests
F
Enterprise | Schedule & Progress | Milestone Completion | Are the projects or services within this enterprise on track? For an Agile enterprise, products and product lines adapt to changing market conditions and customer requirement changes with less schedule slip than standard software development processes. Which ones need management attention (which ones are most behind)? For Agile, | - Enterprise Milestone Status | - Number of milestones started and completed versus plan (percent complete versus plan) | - Milestones mean major milestones or sum of set of milestones - Include updates as schedule changes - For the enterprise, want some early indication of whether major milestones will be met, for each project in the enterprise (or those strategically important or those most at risk)
|  | Enterprise Work Backlog | What is the enterprise work backlog? What should be scheduled next? | - Work Unit Backlog Trends - Burndown Rates | - Work units in backlog by priority level for major item - Work units in backlog resolved | Work units may be: - open stakeholder requests - defects - enhancements, needs - tasks - new contracts, RFPs - deliveries
| Resources & Cost | Financial Performance | Is the enterprise receiving and spending money as planned? Does the enterprise financial process support the needs of the projects? Is the enterprise meeting its goals and objectives? Is the enterprise at risk of exceeding acceptable cost and schedule objectives? | - Funding Availability - Disbursement/Obligation Rate Trends - Earnings Progress - Return on Investment Capital - Cost and Schedule Impact Risk Trends | - Budget, planned, and actual funds available - Disbursements, obligations - Sales, costs, incentive/award fees, taxes - Contribution to overhead - Invested capital, additional revenue - Cost and schedule risk | Is funding available as needed? Consider: - spread of money across the year for multiple projects - color of money and plus-ups for government projects - funding blocks, pull-backs - studies, management reserve, as well as development and maintenance projects
|  | Personnel Effort | Within the enterprise, are there sufficient qualified people to satisfy commitments? | - Staff Level Sufficiency - Effort Distribution and Trends - Workforce Skills Profiles - Workforce Age Profiles - Staff Turnover Rates | - Number of staff within enterprise - Number of staff by skill level and project, needed and assigned to project - Number of staff by age - Staff added, removed, quit | - Both a project and enterprise issue - Skills includes expertise, experience, training, education, and domain knowledge
|  | Facilities and Support Resources | Are needed facilities, equipment, tools, and materials available, across the enterprise? Where should future investments occur? | - Resource availability - Resource utilization | - Quantity needed, available - Time required, available, used - Story deferrals due to resource non availability | For the aggregate set across all projects Indications of resource issues indicated by deferral of epics and stories in the backlog due to lack of appropriate resources for the in-process work
| Product Quality | Functional Correctness | Is the set of projects delivering quality products that meet user expectations? Are known problems being resolved? | - Stakeholder Defects Distribution - Stakeholder Requirements Validation Profile - Warranty Trends | - Defects by status, severity, priority, distribution, etc. - Number of stakeholder requirements Validated Successfully - Warranty claims | Stakeholder defects are those identified after fielding Customer feedback through Agile sprints and reviews should provide rapid reduction in defects in deployed systems
| Process Effectiveness | Process Effectiveness | Are the enterprise processes sufficient to accomplish enterprise objectives? How much rework is occurring? Is the technical risk exposure for the enterprise at an acceptable level? | - Rework Effort Distribution - Rework System Elements Distribution - Portfolio Risk Status | - Schedule and effort expended - total and Rework - Number, types and kinds of risks by status and severity - Epics and Stories returned to backlog for adjustment | - Rework in production might measure waste of production units - Return of Epics an stories to backlog can indicate issues with team execution, but could be an indication of rapid response to changing missions/requirements. - Should consider enterprise risks, in conjunction with assessing aggregate risks across projects
| Technology Effectiveness | Technology Maturity | Does the enterprise have sufficient technology management plans and implementations? Is technology investment in place to ensure adequate leverage of technology into projects? | - Technology investment versus plan - Needs Met by Technology Insertion - Technology Refresh Rate | - Investment amount - Number of needs met by inserted technology - Technologies replaced | - Unlike block upgrades on a platform, agile iterations are launched in a series of sprints, rather than planned and scheduled years in advance, and can be pushed out as they are ready. - Requirements are treated more fluidly and can change over time, enabling technology insertion earlier than in a planned approach.
| Customer Satisfaction | Customer Feedback | How do our customers perceive the enterprise's set of products (product lines)? Are they meeting user expectations? | - Satisfaction Ratings Trends - Market Share - Value for Money (government) - Customer Support requests (cumulative) | - Satisfaction ratings - Enterprise sales, total market sales, new contracts awarded - Assessed value | - Surveys can be conducted at the product epic or story completion for course correction - As a product or product line evolves, customer feedback and satisfaction can be injected into the backlog, and addressed in sprints to rapidly alter the product to meet changing missions.
Customer
Note on E3: Indicators are often trends over time of planned versus actual values. They might also be represented as rates, status as of one date, comparisons between attributes or entities, or other relationships.
Note on F3: In most cases, date/time is captured for each base measure, so is not included in these listings. Most base measures include both planned and actual values.
Note on E29: Indicators are often trends over time of planned versus actual values. They might also be represented as rates, status as of one date, comparisons between attributes or entities, or other relationships.
Note on F29: In most cases, date/time is captured for each base measure, so is not included in these listings. Most base measures include both planned and actual values.

## Sheet1
Level | Information Need | Questions | `Category | Measurable Concept | Measureable Construct | Notes
Team | Product Throughput | are we completing the stories as expected? how long it takes to complete a story? What are my bottlenecks? | Process Performance | Productivity Throughput | Cycle time per story
Team | Are we working to our plan? | Are we working to our plan? | Progress and Schedule | Touch time per story
Team | Is our work correct and complete? |  | Product Quality | Story validated and Verified Is our test coverage adequate automated code testing Code Coverage | Story validated and Verifiied
Program/ Enterprise | Are defect injection rates acceptable? Are defect rates increasing/decreasing? |  |  |  |  | make sure to define what a defect is concern for defects that cross sprint boundaries Defect is a validated story that needed to be corrected after the sprint
Program/ Enterprise | Are we correcting the defects that we find? |  |  |  |  | At the programmer enterprise level
Program/ Enterprise | Are we reducing the number of defects that we create?
| Backlog Volatility due to defects | How much is the backlog changing due to defects? | Product Quality schedule Progress |  | Current number of users stories, added user stories from defects and source
| Backlog Volatility due to external bodies/ influences |  | Size stability schedule Progress |  | Current number of users stories, added user stories from external bodies and source
| Backlog Volatility due to technical debt |  | Product Quality schedule Progress |  | Current number of users stories, added user stories from technical debt | TD is a deliberate shortcut
| Are we delivering business value |  | customer satisfaction | Business value is defined by the Product owner /business owner (can be relative or t-shirt size) | accumulaation of business value by verfified validated story
| Team Engagement Team Morale/ Team satisfaction |  | Process Performance | Measure team participants morale