## DIB_GQM
Category | Goal | Questions | # | Metrics (DoD DIB) | Metrics (Harris rough DRAFT as input to NDIA WG) | Comments
Deployment Rate | Prioritize speed in delivering value to end users through new operational capablities. -Automated development and deployment -Automated testing (unit level, system level) -Iterative deliver-value-now mentality | How quickly can we deliver initial capability for new products? 10 VH; 9 H; | 1 | Time from program launch to deployment of simplest useful functionality. (target 6-12 mo.) | Initial capability cycle time: time from program award (startup review, or SW code start) to completion of initial v1.0 product release from factory (excluding field deployment). (weeks) | Target: 6-12 mo. Measure: calendar weeks (plan vs. actual) Start: program award; End: v1.0 release date May be partial functionality, but must provide useful operational capability to end users. Excludes deployment to field which may not be under contractor control, therefore is not a predictable measure.
|  | How quickly can we add and deliver high priority capabilities for an existing operational product? 12 VH; 7 H; Consider including or adding fixes of operational defects. (Note: for the final table, consider organizing at a higher level to give focus at a top level first) Consider: defect aging | 2a | Time to field high priority functions (spec > ops) (target < 3 mo.) | Incremental capability cycle time: cycle time for release of incremental product capability enhancements (v1.x) Deployment frequency. | Target: <3 mo Measure: calendar weeks (plan vs. actual) Start: sprint start for new operational capability; End:baseline release for validated new operational capability outcome from the factory baseline release. Excludes deployment to field which may not be under contractor control, therefore is not a predictable measure.
|  | How quickly can new security vulnerabilities be patched and deployed to fielded products? 16 vh; 3 H | 2b | Time to fix newly found security hole (find > ops) | Patch cycle time: time for patching a new security vulnerability and releasing a new operational baseline, (v1.x.y)) | Target: <1 wk Measure: calendar days Start: receipt of vendor vulnerability patch; End: release/deployment of patched and verified baseline update. Verification and accreditation of patches is conducted as an outcome of the software factory process. Time from identification of vulnerabillty (e.g., SANS) to availability of patch from the vendor (e.g., Oracle) also impacts overall end user cycle time, but is not under contractor control and is separate from this metric.
|  | What is the "lead time" duration from code committed to a repository to availability of tested functionality? 3 VH; 4 H; 12 M; | 3 | Time from code committed to code in use (target <1 mo) | Factory cycle time: time from final code development submission to CM through factory build, I&T, validation and availability of tested baseline release. | Target: <1 mo Measure: calendar days Start: submission of final code to CM for build; End: baseline release of validated capability ready for operational deployment (outcome from factory). A necessary condition for rapid evolution of delivered SW functionality. Shorter product delivery times demand faster feedback, which enables tighter coupling to user needs. Deployment time to the field is not wholly under contractor control, so is excluded from this metric but does affect availability to users.
What is the cycle time to get a product out?
Response Rate | Quickly detect, isolate, and remove software operational defects. How gracefully SW fails, how many errors are caughtand resolved in testing, and how rapidly developers patch bugs are excellent measures of SW development prowess. | How quickly can a full automated regression test be conducted to verify capability correctness? 9 VH; 7 H; 3 M | 4a | Time required for full regression test (automated) (target <1-7 days) | Regression test cycle time: time to successfully run a complete automated regression test suite. | Target: <1 wk Measure: calendar days Start: start execution of automated regression test; End: successful completion of automated regression test suite.
|  | How quickly can a complete cybersecurity test be successfully completed to ensure adequate resistance to vulnerabilities? 7 VH; 9 H; 3 M Consider: Mean time to attack; mean time to detect; mean time to restore (see DORA DevOps Research Assn metrics, correlation with technical debt). How many IAVAs vulnerability alerts. | 4b | Time required for cybersecurity audit/penetration testing. (target <1-3 mo) | Cybersecurity testing cycle time: time to conduct complete cybersecurity audit/penetration testing. TBD - need input from SSE committee. | Target: <3mo Measure: calendar days Start: start of cybersecurity testing; End: successful completion of cybersecurity testing, resulting in accredited capability release.
|  | What is the reliability and availability of operational service capabilities? Depends on definitions, and customer operational constraints. What actions should be taken as a result? 10 VH; 7 H; 3 M Consider other TPMs, MOEs, KPPs | 5 | Time required to restore service after outage. (target < 1 day) | Mean Time to Repair (MTTR): restoration time from operational outage (duration, in minutes) Outage frequency: trends of # outages per month | Target: MTTR not specified. Varies by program and domain. Typically <30 min. Outage frequency is program-specific; varies by size/scope of the enterprise operations. Measure: MTTR: minutes. Outage frequency: outages/day or month. Start: notification time of outage; End: time that operational capability is restored. This metric applies only in cases where contractor has direct control over operations.
How quickly can we address bug reports from the field?
Code Quality | Ensure high quality code in development and in the field. Find and remove defects in developmental testing where they are most cost-efficient to fix. | Is testing efficiency (e.g., automation, coverage) appropriate relative to project plans? (DIB says 90-100% automated coverage; need a balance) How long does it take to conduct testing within planned constraints? 6 VH; 6 H; 6 M; 1 L Consider: development testing vs. regression testing. Consider relationship betwee #4 and #6. Consider testing operational vs. integration lab) Does new code functionality work as expected and not break previous functionality? 16 VH; 2 H; 1 M | 6 | Automated test coverage of test specs / code (target 100%) | Automated test coverage: % of code specs and functions covered by automated test suite. | Target: >90% (COTS/OS) - 100% (Embedded) automated unit test coverage. The focus is on developmental testing. The automated test suite and test coverage % should be automatically invoked upon commit of code the software factory repository.
|  | What is the quality of code deployed to the field? 10 VH; 9 H | 7 | Number of bugs caught in testing vs.field use. | Defect profile: % of planned vs. actual defects detected in the factory development and testing process vs. field use. Defect removal efficiency: the % of defects detected and removed in-process vs. defect escapes to subsequent life cycle activities. | Target: >75% (COTS/OS) to >90% (embedded) of defects found in developmental testing. Maximize detection and removal of bugs in development where they are much more cost-efficient. Bugs should be prioritized by severity and the trends over time for serious bugs should be monitored and used to drive changes in the test environment and SW development process.
|  | Are product baseline updates reliable in the field such that operational service is not impacted? 5 VH; 8 H; 6 M; 1 L (Consider deployments that are only partially successful. Note that criticality depends on the system and domain, e.g., weapon systems, safety critical) | 8 | Change failure rate (rollback deployed code) | Change failure/rollback rate: % of changes to production that fail, including SW releases and infrastructure changes. | Target: < 10% rollback (COTS/OS), < 1% (embedded). This should include changes that result I ndegraded service or subsequently require remediation, such as those the lead to service impairment our outage, or require a hotfix, rollack, fix-forward, or patch.
|  | Does DoD have data rights to sustain the code baseline? (Acquisition measure - not technical 1 VH; 2 H; 13 M; 2 L) | 9 | % Code available to DoD for inspection/rebuild | N/A - acquirer/customer metric only. % of code delivered to DoD is likely to be program acquisition specific. | Acquirer target is 100% of code delivered to DoD. Per DSB task force recommendations, % of baseline available to DoD is a likely source selection criterion. May be subject to contract-specific with IP constraints for proprietary code generated at company expense.
Program Management, Assessment, and Estimation | Achieve effective insight into management of SW programs, including cost assessment and performance estimation. These metrics describe a list of 'features' (performance metric, contract terms, project plans, activity descriptions) that should be required to provide better tools for monitoring and predicting time, cost, and quality. | Is the code and development platform well structured and maintainable? 7 VH; 10 H; 1 M How much of the code base is newly developed vs. reused from other sources? 0 VH; 5 H; 9 M; 4 L How much capability has been delilvered for each release? 10 VH; 7 H; 1 M; 1 L | 10 | Code structure and complexity measures (size, type, layering) -#/type of specifications (from ALM tools) -structure of code -#/type of deployments -level and type of user engagement -structure of the code base (SW architecture; # of modules, # layers, coupling) -reuse amount of existing code, open source -structure of development environment -programming methodology used (agile, XP, ...) -maturity of the programming org (ISO, CMMI, ...) -structure of the execution platform/environment | Static code analysis measures: # of modules, layers, complexity, coupling, etc. New vs. NDI %: source of code base; new, modified, reused, non-developmental item (COTS, open source, framework, etc.) Estimating parameters/assumptions: TBD - BOEs, estimation model parameters (e.g., SEER, COCOMO), team capability, etc. Other TBD: plenty of other factors that are specific to a given program, proposal, contract, or domain - but they are not necessarily measurable. May vary by acquisition. | Target: not specified; varies by attribute WG needs to consider the intent of this section and consider which measures may be standard across iterative SW programs. Likely to be tailorable by company, domain, etc. Consider also past performance historical data on relevant similar programs as part of source selection.
|  | Are sufficient resources available to execute the SW development plan? (staff, skills, tools, suppliers) 6 VH; 8 H; 4 M How stable are the mission capability requirements? 4 VH; 9 H; 4 M | 11 | Development plan/environment metrics: Structure and type of dev/ops environment. Examples: -# and skill level of programmers on dev team -# of development platforms used -# of subcontractors/vendors used -#/type of user operating environments (platforms) -rate at which major spec functions are delivered -rate of operational env updates (HW refresh rate) -rate of mission env changes (driving code chgs) -# (seats or sites) and skill level of SW users | Staffing profile: qty of SW staff by month, skill levels Dev/test enviroment resources: qty of platforms, license seats, availability for SW staff use; actual vs. plan Training status vs. plan: training delivered vs. plan to ensure adequate SW skill depth and expertise in program technologies, processes, methods Requirements volatility: # of changes to mission requirements/environment vs. time that affect the SW implementation. | Target: not specified; varies by attribute These measures are indicative of SW staff capability, resources, and readiness to perform. Should consider development team, test team, suppliers, SW users, et.
|  | What are appropriate thresholds for SW measures that indicate serious breach relative to baseline plans such that re-evaluation is needed? | 12 | "Nunn-McCurdy" threshold (for any metric). Current Nunn-McCurdy measures of 25% unit cost growth, 50% total program cost growth often will not make sense for continuously developed SW programs. Thresholds may vary according to the defined SW measures and type of SW. | N/A - acquirer/customer metric only | Target: 1.1X for COTS; 1.25X for customized SW; 1.5X for COTS HW/OS; 1.5X for Custom (real-time) HW/SW. Guidelines should be provided for each key performance-based measure levied in source selection for when re-evaluation is needed.
|  | Is the integration and test progress proceeding as planned? Are the capabilities and features being implemented and completed as planned? |  | (Capability burnup; capabilities, features)

## DIB_PSM_QuestionRanking
Category (DIB) | Goal (Derived from DIB by PSM/NDIA) | Questions (derived from DIB by PSM/NDIA; see GQM table for details) | VH | H | M | L | Total
Deployment Rate | Prioritize speed in delivering value to end users through new operational capablities. -Automated development and deployment -Automated testing (unit level, system level) -Iterative deliver-value-now mentality | How quickly can we deliver initial capability for new products? | 10 | 9 |  |  | 19
|  | How quickly can we add and deliver high priority capabilities for an existing operational product? | 12 | 7 |  |  | 19
|  | How quickly can new security vulnerabilities be patched and deployed to fielded products? | 16 | 3 |  |  | 19
|  | What is the "lead time" duration from code committed to a repository to availability of tested functionality? | 3 | 4 | 12 |  | 19
|  | What is the cycle time to get a product out? (TBD) |  |  |  |  | 0
Response Rate | Quickly detect, isolate, and remove software operational defects. How gracefully SW fails, how many errors are caughtand resolved in testing, and how rapidly developers patch bugs are excellent measures of SW development prowess. | How quickly can a full automated regression test be conducted to verify capability correctness? | 9 | 7 | 3 |  | 19
|  | How quickly can a complete cybersecurity test be successfully completed to ensure adequate resistance to vulnerabilities? | 7 | 9 | 3 |  | 19
|  | What is the reliability and availability of operational service capabilities? | 10 | 7 | 3 |  | 20
|  | How quickly can we address bug reports from the field? (TBD) |  |  |  |  | 0
Code Quality | Ensure high quality code in development and in the field. Find and remove defects in developmental testing where they are most cost-efficient to fix. | Is testing efficiency (e.g., automation, coverage) appropriate relative to project plans? How long does it take to conduct testing within planned constraints? | 6 | 6 | 6 | 1 | 19
|  | Does new code functionality work as expected and not break previous functionality? | 16 | 2 | 1 |  | 19
|  | What is the quality of code deployed to the field? | 10 | 9 |  |  | 19
|  | Are product baseline updates reliable in the field such that operational service is not impacted? | 5 | 8 | 6 | 1 | 20
|  | Does DoD have data rights to sustain the code baseline? | 1 | 2 | 13 | 2 | 18
Program Management, Assessment, and Estimation | Achieve effective insight into management of SW programs, including cost assessment and performance estimation. These metrics describe a list of 'features' (performance metric, contract terms, project plans, activity descriptions) that should be required to provide better tools for monitoring and predicting time, cost, and quality. | Is the code and development platform well structured and maintainable? | 7 | 10 | 1 |  | 18
|  | How much of the code base is newly developed vs. reused from other sources? | 0 | 5 | 9 | 4 | 18
|  | How much capability has been delilvered for each release? | 10 | 7 | 1 | 1 | 19
|  | Are sufficient resources available to execute the SW development plan? (staff, skills, tools, suppliers) | 6 | 8 | 4 |  | 18
|  | How stable are the mission capability requirements? | 4 | 9 | 4 |  | 17
|  | What are appropriate thresholds for SW measures that indicate serious breach relative to baseline plans such that re-evaluation is needed? (TBD) |  |  |  |  | 0
|  | Is the integration and test progress proceeding as planned? (TBD) Are the capabilities and features being implemented and completed as planned? (TBD) |  |  |  |  | 0

## PSM_MeasureScoring
| Points: | 10 | 8 | 6 | 5 | 4 | 2 | 0
| Candidate or Example SW Metrics Proposed by DSB and DIB: Good standard SW measure? | Strongly Agree | Agree | Somewhat Agree | Neutral | Somewhat Disagree | Disagree | Strongly Disagree | Total Voters | Weighted Score | In Common Use? | Usage %
DSB | Sprint Burndown | 2 | 6 | 5 | 2 | 4 | 2 |  | 21 | 6.0952 | 8 | 38.1%
| Epic and Release Burndown | 4 | 8 | 6 | 3 |  |  |  | 21 | 7.381 | 8 | 38.1%
| Velocity | 2 | 6 | 9 | 2 | 1 | 1 |  | 21 | 6.5714 | 6 | 28.57%
| Cycle Time (Control Chart) | 1 | 4 | 9 | 2 | 2 | 2 |  | 20 | 5.9 | 2 | 10%
| Cumulative Flow Diagram |  | 1 | 9 | 7 | 2 | 1 |  | 20 | 5.35 | 1 | 5%
DIB | Time from program launch to deployment of simplest useful functionality | 3 | 7 | 6 | 3 |  |  |  | 19 | 7.2105 | 2 | 10.53%
| Time to field high priority functions (spec > ops) | 3 | 9 | 6 | 1 |  |  |  | 19 | 7.5263 | 0 | 0%
| Time to fix newly found security hole (find > ops) | 6 | 9 | 3 | 2 |  | 1 |  | 21 | 7.7143 | 4 | 19.05%
| Time from code committed to code in use |  | 7 | 6 | 2 | 3 | 2 |  | 20 | 5.9 | 4 | 20%
| Time required for full regression test (automated) | 1 | 8 | 5 | 4 | 1 | 1 |  | 20 | 6.5 | 4 | 20%
| Time required to restore service after outage | 5 | 5 | 4 | 1 | 1 |  |  | 16 | 7.6875 | 11 | 68.75%
| Automated test coverage of test specs / code |  | 10 | 4 | 2 | 4 |  |  | 20 | 6.5 | 2 | 10%
| Number of bugs caught in testing vs. field use | 8 | 11 | 1 | 1 |  |  |  | 21 | 8.5238 | 9 | 42.86%
| Change failure rate (rollback deployed code) |  | 12 | 2 | 5 | 1 |  |  | 20 | 6.85 | 9 | 45%
Note on K2: Author: Array formulas; use CTRL-SHIFT-ENTER